## Sheet1
REF | DRG No. | DESCRIPTION | QTY | Total (x16) | REVISION | MATERIAL | PRT/ASM | Received | Delivery LLO (missing) | Delivery LHO (missing) | Status | Notes | Documention status
1 | 1-4-20_WASHER | 1/4" 20 UNC WASHER | 30 | 480 | A | ST. STEEL | PART
2 | 1-4_20X0-5D_UNC_THREAD_INSERT | 1/4-20 x 0.5D UNC THREAD INSERT | 2 | 32 | A | NITRONIC 60 | PART |  | have 300 | have 300
3 | 1-4_20X1-5D_UNC_THREAD_INSERT | 1/4-20 x 1.5D UNC THREAD INSERT | 251 | 4016 | A | NITRONIC 60 | PART |  | have 300 | have 300
4 | 1-4_20X1D_UNC_THREAD_INSERT | 1/4-20 x 1D UNC THREAD INSERT | 70 | 1120 | A | NITRONIC 60 | PART |  | have 600 | have 600
5 | 1-4_20_UNC_1-00INCH | 1/4" 20 UNC X 1" CAP HEAD | 217 | 3472 | J | ST. STEEL | PART
6 | 1-4_20_UNC_1-00INCH_ROUND_ | 1/4" 20 UNC X 1" CAP HEAD, SPHERICAL TIP | 4 | 64 | A | ST. STEEL | PART | 350 |  |  | Delivered
7 | 1-4_20_UNC_1-00INCH_SIL_PLT | 1/4" 20 UNC X 1" CAP HEAD SILVER PLATED | 226 | 3616 | A | SIL PLTD | PART | 8000 |  |  | Delivered
8 | 1-4_20_UNC_1-25INCH | 1/4" 20 UNC X 1.25" CAP HEAD | 8 | 128 | A | ST.STEEL | PART
9 | 1-4_20_UNC_1-5INCH | 1/4-20 UNC X 1.5" CAP HEAD | 32 | 512 | J | ST. STEEL | PART
10 | 1-4_20_UNC_2-00INCH | 1/4" 20 UNC X 2" CAP HEAD | 24 | 384 | A | ST. STEEL | PART
11 | 1-4_20_UNC_2-00INCH_ROUND | 1/4" 20 UNC X 2" CAP HEAD, SPHERICAL TIP | 117 | 1872 | J | ST. STEEL | PART | 2000 |  |  | Delivered
12 | 1-4_20_UNC_2-00INCH_SIL_PLT | 1/4" 20 UNC X 2" CAP HEAD SILVER PLATED | 32 | 512 | A | SIL PLTD | PART | 750 |  |  | Delivered
13 | 1-4_20_UNC_2-50INCH_ROUND | 1/4" 20 UNC X 2.5" CAP HEAD, SPHERICAL TIP | 8 | 128 | A | ST. STEEL | PART | 350 |  |  | Delivered
14 | 1-4_20_UNC_NUT__ | 1/4 20 UNC NUT | 135 | 2160 | A | ST. STEEL | PART
15 | 1-4_20_UNC_X_0-188_GRUBSCREW | 1/4" 20 UNC X 0.188" GRUBSCREW | 4 | 64 | A | ST. STEEL | PART
16 | 1-4_SPERICAL_WASHER | 1/4 SPHERICAL WASHER | 8 | 128 | A | ST. STEEL | PART
17 | 2-56_UNC_0-375INCH | 2-56 UNC X .375" CAP HEAD | 20 | 320 | A | ST. STEEL | PART
18 | 3-8_16X1-5D_UNC_THREAD_INSERT | 3/8-16 x 1.5D UNC THREAD INSERT | 36 | 576 | A | NITRONIC 60 | PART
19 | 3-8_16X1D_UNC_THREAD_INSERT | 3/8-16 x 1D UNC THREAD INSERT | 16 | 256 | A | NITRONIC 60 | PART
20 | 3-8_16_UNC_1-25INCH | 3/8 16 UNC X 1.25" CAP HEAD | 48 | 768 | J | ST. STEEL | PART
21 | 3-8_16_UNC_1-75_INCH | 3/8-16 UNC X 1.75" CAP HEAD | 24 | 384 | A | ST. STEEL | PART
22 | 3-8_16_UNC_2-25INCH | 3/8" 16 UNC X 2.25" CAP HEAD | 8 | 128 | J | ST. STEEL | PART
23 | 3-8_16_UNC_3-00INCH | 3/8-16 UNC X 3.0" CAP HEAD | 8 | 128 | A | ST. STEEL | PART
24 | 3-8_INCH_WASHER | 3/8 FLAT WASHER | 8 | 128 | A | ST. STEEL | PART
25 | 3-8_SPHERICAL_WASHER | 3/8 SPHERICAL WASHER | 8 | 128 | J | ST. STEEL | PART
26 | 8-32X1-5D_UNC_THREAD_INSERT | 8-32 x 1.5D UNC THREAD INSERT | 216 | 3456 | A | NITRONIC 60 | PART |  |  |  |  | received 1.0D (300 to eacah site)
27 | 8-32_UNC_0-5INCH | 8-32 UNC X 0.5" CAP HEAD | 8 | 128 | A | ST. STEEL | PART
28 | 8-32_UNC_0-625INCH | 8-32 UNC X 0.625" CAP HEAD | 334 | 5344 | A | ST. STEEL | PART
29 | 8-32_UNC_0-625INCH_SIL_PLT | 8-32 UNC X 0.625" CAP HEAD | 28 | 448 | - | SIL PLTD | PART | 6000 |  |  | Delivered
30 | 8-32_UNC_0-875INCH | 8-32 UNC X 0.875" CAP HEAD | 48 | 768 | A | ST. STEEL | PART
31 | 8-32_UNC_1-50INCH | 8-32 UNC X 1.5" CAP HEAD | 8 | 128 | A | ST. STEEL | PART
32 | 8-32_UNC_BIG_WASHER | 8-32 UNC WASHER washer 9.5 OD | 16 | 256 | A | ST. STEEL | PART
34 | D000069 | LIGO 1 OSEM | 4 | 64 | A | AS DRW | PART
35 | D060310 | TABLECLOTH | 1 | 16 | F | AS DRW | ASSEMBLY
36 | D060311 | FRONT AND REAR PLATE | 2 | 32 | C | AL ALLOY | PART |  |  |  | LLO/LHO swap
37 | D060312 | RIGHT HAND PLATE | 1 | 16 | E | AL ALLOY | PART
38 | D060313 | TOP PLATE | 2 | 32 | C | AL ALLOY | PART
39 | D060314 | LEFT HAND PLATE | 1 | 16 | E | AL ALLOY | PART
40 | D060315 | TABLECLOTH PINCH PLATE | 4 | 64 | C | AL ALLOY | PART
41 | D060316 | OSEM AND ECD ADJUSTER | 8 | 128 | E | AS DRW | ASSEMBLY
42 | D060317 | ECD STATIC BLOCK | 16 | 256 | D | OFHC COPPER | PART |  | Missing all | Missing all | Need modification
43 | D060318 | OSEM AND ECD MOUNTING BRACKET | 8 | 128 | E | AL ALLOY | PART
44 | D060320 | OSEM ADJUSTMENT PLATE | 2 | 32 | E | AS DRW | ASSEMBLY
45 | D060321 | POSITION ADJUSTER FOR | 2 | 32 | D | AL ALLOY | PART
46 | D060322 | TRANSVERSE OSEM ADJUSTER | 2 | 32 | D | AS DRW | ASSEMBLY
47 | D060323 | TRANSVERSE OSEM POSITION | 2 | 32 | E | AL ALLOY | PART |  |  |  | found at LLO
48 | D060324 | BLADE CARTRIDGE | 4 | 64 | G | AS DRW | ASSEMBLY
49 | D060325 | ROTATIONAL ADJUSTER | 4 | 64 | E | ST ST | PART |  |  | Missing 4 | Correct in contract
50 | D060328 | 3/8-16 UNC T NUT | 8 | 128 | E | ST STEEL | PART
51 | D060329 | TOP STAGE STIFF BACK | 4 | 64 | D | AL ALLOY | PART |  | Missing all | Missing all | Need modification
52 | D060330 | ROTATIONAL ADJUSTER | 4 | 64 | E | ST STEEL | PART |  | Missing all | Missing all | Check status
53 | D060331 | JACKING SCREW / EARTHQUAKE STOP | 4 | 64 | E | ST STEEL | PART
54 | D060332 | WIRE CLAMP | 4 | 64 | F | ST. STEEL | ASSEMBLY
55 | D060333 | WIRE CLAMP BODY, TOP STAGE | 4 | 64 | E | ST STEEL | PART
56 | D060334 | WIRE CLAMP JAW | 20 | 320 | J | ST STEEL | PART
57 | D060335 | RECESSED 1/4" 20 UNC | 40 | 640 | J | ST STEEL | PART
58 | D060336 | 2MM CAM | 56 | 896 | H | PH BRONZE | PART
59 | D060337 | PENULTIMATE MASS WIRE CLAMP | 8 | 128 | H | AS DRW | ASSEMBLY
60 | D060338 | ROUND MASS WIRE CLAMP PLATE | 8 | 128 | F | ST. STEEL | PART
61 | D060340 | ROUND MASS CLAMP JAW | 20 | 320 | F | ST. STEEL | PART
62 | D060341 | PENULTIMATE REACTION MASS | 1 | 16 | G | AS DRW | ASSEMBLY
63 | D060342 | CENTRAL MASS | 1 | 16 | F | ST STEEL | PART |  |  | Missing 1 | Correct in contract
64 | D060343 | FRONT PLATE | 1 | 16 | F | ST STEEL | PART
65 | D060344 | BACK PLATE | 1 | 16 | H | ST STEEL | PART
66 | D060348 | OSEM TRANSLATION PLATE | 4 | 64 | E | AL ALLOY | PART |  |  | Missing 4 | Correct in contract
67 | D060349 | LIGO 1 OSEM MOUNT | 4 | 64 | G | AS DRW | ASSEMBLY
68 | D060350 | CONTROL RING | 4 | 64 | E | AL ALLOY | PART |  |  | Missing 8 | Correct in contract
69 | D060351 | BASE PLATE | 4 | 64 | E | AL ALLOY | PART |  |  | Missing 4 | Correct in contract
70 | D060352 | PITCH MASS | 1 | 16 | G | AS DRW | ASSEMBLY
71 | D060353 | PEN RE PITCH MASS | 1 | 16 | F | ST. STEEL | PART
72 | D060354 | CLAMPING COLLAR | 1 | 16 | E | PH BRONZE | PART
73 | D060355 | DUMMY TEST MASS | 2 | 32 | J | AS DRW | ASSEMBLY
74 | D060356 | DUMMY TEST REACTION MASS | 1 | 16 | G | AS DRW | ASSEMBLY
75 | D060357 | HALF MASS | 2 | 32 | G | AL. ALLOY | PART
76 | D060358 | DUMMY TEST MASS SIDE | 4 | 64 | G | AL ALLOY | PART
77 | D060375 | UI MASS | 2 | 32 | K | AS BOM | ASSEMBLY
78 | D060376 | MASS BASE PLATE | 2 | 32 | J | ST STEEL | PART
79 | D060377 | BLADE TIP Z POSITION ADJ | 4 | 64 | G | AL ALLOY | PART
80 | D060378 | BLADE TIP Z POSITION ADJ | 4 | 64 | H | ST STEEL | PART
81 | D060379 | OSEM AND FLAG COUNTERWEIGHT | 8 | 128 | H | ST STEEL | PART
82 | D060381 | UI MASS BLADE ECD | 4 | 64 | G | OFHC COPPER | PART |  |  |  | LLO/LO trade
83 | D060382 | UI MASS TOP PLATE | 4 | 64 | H | ST STEEL | PART
84 | D060383 | MIDDLE WIRE, WIRE CLAMP | 4 | 64 | H | ST STEEL | PART
85 | D060384 | MIDDLE WIRE WIRE CLAMP | 4 | 64 | J | SEE ITEMS LIST | ASSEMBLY
86 | D060385 | UI MASS FLAG MOUNT | 5 | 80 | J | SEE ITEMS LIST | ASSEMBLY
87 | D060386 | MOUNT BLOCK | 4 | 64 | H | ST STEEL | PART
88 | D060387 | UI MASS OSEM MOUNT | 4 | 64 | K | SEE ITEMS LIST | ASSEMBLY
89 | D060388 | BRACKET | 4 | 64 | K | AL ALLOY | PART |  |  |  | LLO/LHO trade
90 | D060389 | ADJUSTER | 4 | 64 | J | AL ALLOY | PART |  |  | Missing 4 | Correct in contract
91 | D060390 | WIRE CLAMP BODY | 4 | 64 | H | ST STEEL | PART
92 | D060391 | TOP WIRE CLAMP | 4 | 64 | J | SEE ITEMS LIST | ASSEMBLY
93 | D060392 | MAGNET RETAINER | 4 | 64 | H | STAINLESS STEEL | PART |  |  | Missing 4 | Correct in contract
94 | D060393 | UI MASS MAGNET AND FLAG MOUNT | 4 | 64 | H | N/A | ASSEMBLY
95 | D060394 | SPACER | 4 | 64 | G | AL ALLOY | PART |  |  | Missing 4 | Correct in contract
96 | D060395 | WIRE CLAMP BODY | 4 | 64 | H | ST.STEEL | PART
97 | D060397 | TOP MASS SPACER | 16 | 256 | H | ST. STEEL | PART
98 | D060398 | PITCH ADJUSTER & MASS | 8 | 128 | H | AL ALLOY | PART |  | Missing all (?) | Missing 2
99 | D060399 | STOP BRIDGE | 16 | 256 | G | AL ALLOY | PART
100 | D060400 | OSEM MAGNET FLAG | 16 | 256 | G | ALUMINIUM | PART |  | Need 6 |  | At RAL - Need to send
101 | D060401 | MAGNETIC PLUG | 108 | 1728 | G | STAINLESS STEEL | PART
102 | D060403 | TOP MASS PRODUCTION GA | 2 | 32 | K | AS BOM | ASSEMBLY
103 | D060405 | PITCH ADJUSTER | 4 | 64 | H | ST. STEEL | PART
104 | D060406 | BASE PLATE STIFFENER | 4 | 64 | G | AL ALLOY | PART
105 | D060407 | OSEM & ECD UNIT BACKBONE | 8 | 128 | G | AL ALLOY | PART
106 | D060408 | ECD MAGNET MOUNT PLATE | 16 | 256 | G | AL ALLOY | PART
107 | D060409 | OSEM ECD UNIT | 8 | 128 | H | AS DRW | ASSEMBLY
108 | D060410 | OSEM MAGNET ASSEMBLY | 16 | 256 | G | SEE ITEMS LIST | ASSEMBLY
109 | D060411 | TOP PLATE | 4 | 64 | K | ST. STEEL | PART
110 | D060412 | OSEM BRACKET (TOP OSEM) | 2 | 32 | G | AL ALLOY | PART
111 | D060413 | 1/4" 20 UNC X 1" CAP HEAD | 16 | 256 | H | ST. STEEL | PART
112 | D060414 | BLADE TiP Z POSITION ADJ | 4 | 64 | G | AL ALLOY | PART
113 | D060415 | BLADE TIP Z POSITION ADJ | 4 | 64 | H | ST STEEL | PART
114 | D060416 | OSEM MAGNET AND FLAG | 12 | 192 | H | AS DRAWING | ASSEMBLY
115 | D060417 | OSEM MAGNET AND FLAG CONCEPT | 4 | 64 | H | AS BOM | ASSEMBLY
116 | D060418 | MAGNET RETAINER | 16 | 256 | H | STAINLESS STEEL | PART
117 | D060419 | TOP MASS WIRE CLAMP | 4 | 64 | J | AS DRW | ASSEMBLY
118 | D060420 | WIRE CLAMP ADJUSTMENT BLOCK | 4 | 64 | H | AL ALLOY | PART |  |  | Missing 4 | Correct in contract
119 | D060421 | MASS AND SUPPORT MEMBER | 4 | 64 | H | ST. STEEL | PART |  |  | Missing 8 | Correct in contract
120 | D060422 | UI MASS WIRE CLAMP | 4 | 64 | H | AS DRW | ASSEMBLY
121 | D060426 | UI MASS WIRE CLAMP BODY | 4 | 64 | G | ST. STEEL | PART |  | Missing all | Missing all | Where are these?
122 | D060430 | BASE PLATE | 2 | 32 | J | ST.STEEL | PART |  | Missing all | Missing all | Re-make… wrong material
123 | D060434 | OUTER FACE PLATE | 2 | 32 | G | ALUMINIUM ALLOY | PART |  | Missing all | Missing all | Mods… drawings still need mod
124 | D060444 | BASE BAR - LONG | 2 | 32 | C | AL. ALLOY | PART
125 | D060445 | BUSH | 8 | 128 | B | PFA 440 HP | PART
126 | D060446 | ADJUSTABLE PAD ASSEMBLY | 2 | 32 | C | AS DRW | ASSEMBLY
127 | D060447 | ADJUSTABLE PAD JAW | 2 | 32 | B | AL. ALLOY | PART
128 | D060448 | PIN | 8 | 128 | C | ST. STEEL | PART
129 | D060449 | ADJUSTABLE PAD | 2 | 32 | B | PFA 440 HP | PART |  | Too many? | Too many? | Betsy to check
130 | D060450 | SPACER # 4 | 8 | 128 | B | AL. ALLOY | PART |  | All + Other sizes | All + Other sizes | Awaiting dims from Monolithic
131 | D060454 | INNER LOWER STRUCTURE | 1 | 16 | D | AS DRW | ASSEMBLY
132 | D060455 | LOWER STRUCTURE X-BRACE | 2 | 32 | B | AL ALLOY | PART |  |  |  | Poor finish - send spares
133 | D060457 | ADJUSTABLE PAD ASSEMBLY SHORT | 2 | 32 | C | SEE PARTS LIST | ASSEMBLY
134 | D060458 | BASE BAR | 2 | 32 | C | AL. ALLOY | PART |  | 2 | 20 | Correct in contract
135 | D060459 | ADJUSTABLE PAD JAW | 2 | 32 | B | AL. ALLOY | PART
136 | D060460 | ADJUSTABLE PAD | 2 | 32 | B | PFA 440 HP | PART |  | Missing 2 |  | Correct in contract
137 | D060461 | PEN TEST MASS PAD | 2 | 32 | C | PFA 440 HP | PART |  | Missing 12 | Missing 20 | Correct in contract
138 | D060462 | INNER FACE PLATE | 2 | 32 | G | ALUMINIUM ALLOY | PART |  | Missing all | Missing all | Modifications required
139 | D060475 | EARTHQUAKE-STOP MOUNTS-LONG | 6 | 96 | D | AL ALLOY | PART
140 | D060476 | EARTHQUAKE-STOP MOUNTS-SHORT | 6 | 96 | C | AL ALLOY | PART
141 | D060477 | PENULTIMATE MASS LWR STOP MT 1 | 2 | 32 | C | AL. ALLOY | PART
142 | D060478 | PENULTIMATE MASS LWR STOP MT 2 | 2 | 32 | B | AL. ALLOY | PART
143 | D060479 | PEN RE MASS PAD | 2 | 32 | B | PFA 440 HP | PART
144 | D060481 | ROUND MASS FRONT STOP | 16 | 256 | C | AL. ALLOY | PART
145 | D060492 | UPPER STRUCTURE WELDMENT | 1 | 16 | A | SEE NOTE | ASSEMBLY
146 | D060499 | REMOVEABLE CROSS MEMBER | 2 | 32 | A | AL ALLOY | PART
147 | D060544 | EARTHQUAKE STOP ASSY | 36 | 576 | A | N/A | ASSEMBLY
148 | D060545 | EARTQUAGE STOP ADJUSTER | 36 | 576 | A | ST STEEL | PART |  | Missing all | Missing all | Not in contract
149 | D060546 | EARTHQUAKE STOP | 36 | 576 | A | FLOUREL | PART |  | Missing all | Missing all | Not in contract
150 | D060547 | EARTHQUAKE STOP MOUNT PLATE | 36 | 576 | A | ST STEEL | PART |  | Missing all | Missing all | Not in contract
151 | D060548 | FUSED SILICA EARTHQUAKE STOP | 44 | 704 | A | FUSED SILICA | PART |  | Missing all | Missing all | Not in contract
152 | D070008 | SPACING PLUG | 8 | 128 | B | AL ALLOY | PART
153 | D070056 | QUAD DOG CLAMP | 16 | 256 | A | ST STEEL | PART |  | Missing 90 |  | Non OJEU
154 | D070140 | TOP STAGE BLADE WIRE CLAMP SHIM | 20 | 320 | B | AL ALLOY | PART
155 | D070214 | TOP RING WIRE CLAMP | 1 | 16 | A | AS DRW | ASSEMBLY
156 | D070215 | WIRE CLAMP BODY | 1 | 16 | A | AL ALLOY | PART |  | Need all | Need all | New
157 | D070216 | UPPER STRUCTURE STAY WIRE CLAMP | 1 | 16 | A | AL ALLOY | PART
158 | D070217 | UPPER STRUCTURE STAY WIRE CLAMP | 1 | 16 | A | AS DRW | ASSEMBLY
159 | D070218 | MASS WIRE CLAMP #1 | 3 | 48 | A | AS DRW | ASSEMBLY
160 | D070219 | MASS WIRE CLAMP BASE | 3 | 48 | A | AL ALLOY | PART |  | Need all | Need all | New
161 | D070220 | UIM MASS TOP WIRE CLAMP | 1 | 16 | A | AL ALLOY | PART |  | Need all | Need all | New
162 | D070221 | UIM MASS TOP WIRE CLAMP | 1 | 16 | A | AS DRW | ASSEMBLY
163 | D070222 | PEN RE MASS CABLE CLAMP | 1 | 16 | A | AS DRW | ASSEMBLY
164 | D070223 | PEN RE MASS WIRE CLAMP | 1 | 16 | A | AL ALLOY | PART |  | Need all | Need all | New
165 | D070224 | MASS SIDE WIRECLAMP BODY | 2 | 32 | A | AL ALLOY | PART |  | Need all | Need all | New
166 | D070225 | MASS WIRE CLAMP | 2 | 32 | A | AS DRW | ASSEMBLY
167 | D070226 | CABLE CLAMP JAW | 10 | 160 | A | AL ALLOY | PART |  | Need all | Need all | New
168 | D070234 | PEN RE MASS MAGNETS | 1 | 16 | B | AS DRW | ASSEMBLY
169 | D070235 | MAGNET HOLDER | 4 | 64 | E | AL ALLOY | PART |  | Need all | Need all | New
170 | D070236 | PENULTIMATE MASS FLAG MOUNT | 1 | 16 | B | AL ALLOY | PART |  | Need all | Need all | New
171 | D070237 | MAGNET BASE | 4 | 64 | E | AL/ALLOY | PART |  | Need all | Need all | New
172 | D070238 | STEEL DISK | 12 | 192 | E | ST.STEEL | PART |  | Need all | Need all | New
173 | D070247 | TABLECLOTH PADS | 4 | 64 | A | AL ALLOY | PART
174 | D070538 | IMPLEMENTATION RING | 1 | 16 | A | AL ALLOY | PART |  | Need all | Need all | Non OJEU
175 | D070539 | IMPLEMENTATION RING | 1 | 16 | A | AL ALLOY | PART |  | Need all | Need all | Non OJEU
176 | D070540 | UIM TC E'QUAKE STOP ASSY #1 | 1 | 16 | D | AS DRW | ASSEMBLY
177 | D070541 | UIM RC E'QUAKE STOP ASSY #1 | 1 | 16 | D | AS DRW | ASSEMBLY
178 | D070542 | UIM RC E'QUAKE STOP ASSY #2 | 1 | 16 | D | AS DRW | ASSEMBLY
179 | D070543 | UIM TC E'QUAKE STOP ASSY #2 | 1 | 16 | D | AS DRW | ASSEMBLY
180 | D070544 | TEST CHAIN UIM STOP | 1 | 16 | D | AL ALLOY | PART |  | Missing all | Missing all | Correct in contract
181 | D070545 | TEST CHAIN UIM STOP | 1 | 16 | C | AL ALLOY | PART
182 | D070546 | REACTION CHAIN UIM STOP | 1 | 16 | C | AL ALLOY | PART
183 | D070547 | REACTION CHAIN UIM STOP | 1 | 16 | C | AL ALLOY | PART
184 | D070548 | UIM MASS STOP | 4 | 64 | C | AL ALLOY | PART
185 | D070549 | UIM E'QUAKE STOP | 8 | 128 | A | ST STEEL | PART
186 | D070552 | ITM/ETM SLEEVE | 1 | 16 | E | AL ALLOY | PART |  |  |  | LHO has 1
187 | D080166 | ITM OSEM CAN | 4 | 64 | E | AS DRW | ASSEMBLY
188 | D080167 | CAN FRONT PLATE | 4 | 64 | A | ST.STEEL | PART
189 | D080168 | CAN BODY | 4 | 64 | D | ST STEEL | PART
190 | D080240 | PEN RE MASS BUMP STOP ASM | 4 | 64 | E | AS DRW | ASSEMBLY
191 | D080241 | EARTHQUAKE STOP ASSY | 4 | 64 | A | AS DRW | ASSEMBLY
192 | D080242 | MODIFIED 1/4-20 UNC X 1" HEX HEAD | 4 | 64 | E | ST. STEEL | PART |  | Need all | Need all | New
193 | D080243 | EARTHQUAKE STOP MOUNT PLATE | 4 | 64 | D | ST STEEL | PART |  | Need all | Need all | New
194 | D080244 | EARTHQUAKE STOP MOUNT PLATE | 4 | 64 | A | ST STEEL | PART |  | Need all | Need all | New
195 | D080245 | EARTHQUAKE STOP | 8 | 128 | D | FLOUREL | PART |  | Need all | Need all | New
196 | D090433 | TRANSPORT PADS | 6 | 96 | A | PFA 440 HP | PART |  | Need all | Need all | New
197 | D090434 | FRONT TRANSPORT PAD | 12 | 192 | A | PFA 440 HP | PART |  | Need all | Need all | New
198 | D090438 | RINGHEATER ATTACHMENT PIECE | 4 | 64 | A | AL ALLOY | PART |  | Missing all | Missing all | At RAL - send!
199 | D0901342 | LS - SLEEVE INTERFACE WEDGE 1 | 16 | 256 | A | AL ALLOY | PART |  | Need all | Need all | Not designed
200 | D0901343 | LS - SLEEVE INTERFACE WEDGE 2 | 16 | 256 | A | AL ALLOY | PART |  | Need all | Need all | Not designed
201 | D0901344 | 10MM DIA X 10MM MAGNET | 92 | 1472 | A | AS PAR SPEC | PART
202 | D0901345 | 2MM DIA X 6MM MAGNET | 8 | 128 | B | AS PER SPEC | PART
203 | D0901346 | QUAD N-PTYPE ITM | 1 | 16 | B | AS DRW | ASSEMBLY
204 | D0901439 | TOP STAGE STIFF BACK | 4 | 64 | - | AL ALLOY | PART |  | Missing all | Missing all | Check status
205 | D0901933 | LS BRACKET ATTACHMENT PIN | 1 | 16 | A | ST.STEEL | PART |  | Missing all | Missing all
206 | D060235_FLAT | TOP STAGE BLADES | 4 | 64 | D | MARAGING STEEL | 250 PART
207 | D060236_FLAT | MIDDLE BLADE SPRING | 4 | 64 | C | MARAGING STEEL | 250 PART
208 | D060237_FLAT | BOTTOM BLADE SPRINGS | 4 | 64 | C | MARAGING STEEL | 250 PART
209 | D060326-000 | BLADE CLAMP | 4 | 64 | E | ST. STEEL | PART |  | Missing all | Missing all | Check status
210 | D060327_000 | BLADE CLAMP | 4 | 64 | E | ST STEEL | PART |  | Missing all | Missing all | Check status
211 | D060359-050_0 | ADDITIONAL MASS | 65 | 1040 | F | ST STEEL | PART
212 | D060359-100_0 | ADDITIONAL MASS | 39 | 624 | F | ST STEEL | PART
213 | D060380-000 | BLADE CLAMP | 4 | 64 | H | ST. STEEL | PART |  | Missing all | Missing all | Check status | Check if we are acutally missing all… may only be 4
214 | D060404-000 | BLADE CLAMP | 4 | 64 | H | ST. STEEL | PART
215 | OSEM | BIRMINGHAM OSEM | 12 | 192 | A | AS DRW | ASSEMBLY
216 | WIRE_0-457_DIA | FINAL WIRE | 1 | 16 | A | HARD DRAWN STEEL | PART
217 | WIRE_0-635_DIA | BOTTOM WIRE | 1 | 16 | A | HARD DRAWN STEEL | PART
218 | WIRE_0-71MM_DIA | MIDDLE WIRE | 1 | 16 | A | HARD DRAWN STEEL | PART
219 | WIRE_1-1MM_DIA | TOP WIRE | 1 | 16 | A | HARD DRAWN STEEL | PART
|  | Total parts | 3407