## Slide 1: Status of the H1 Squeezer Experiment
Excomm meeting, July 20, 2009
Daniel Sigg, LIGO Hanford Observatory
ANU, AEI, MIT, CIT and LHO collaboration

## Slide 2: Highlights
Graduate students Sheila D. (MIT) and Sheon C. (ANU)
OPO development at ANU
  6 dB of squeezing observed
  Traveling wave bowtie design works
AEI loaner SHG at MIT
  In the process of building our own (copy AEI design)
Laser, optical table and clean room installed at MIT
Noise model in development
Electronics design done for RF distribution
  Shared with advanced LIGO
Next progress review in August

## Slide 3: Block Schematics
Interferometer
Laser
Auxiliary
Laser
SHG
OPO
Homodyne Detector
Faraday
OMC
Fiber
Squeezer
AS Port
S
0
S
1
S
4
S
5
S
2
S
3
DC

## Slide 4: ANU Traveling Wave OPO
Oven/
Temperature
Sensor
Crystal
Squeezing
Out
Pump light In
PZT Actuator
200 mm
150 mm

## Slide 5: Lab at ANU
Main Laser
SHG
OPO
Homodyne
Main-Aux
Phase lock
Auxiliary Laser

## Slide 6: Squeezing Performance
Electronics
Mains harmonics
Cross coupling from Coherent Lock
Electronic Noise?
Lab environment
Acoustic Noise
8dB
6dB
Quantum noise
Observed squeezing
Inferred squeezing

## Slide 7: Optical Layout

## Slide 8: Schedule
ANU/OPO well on track
Noise model (remaining action item from review) will be completed in a ~month
AEI homodyne detector will be shipped to ANU ahead of schedule
Assembly at MIT
  Optical layout on track
  Parts late by ~2 months (initial funds almost exhausted)
Electronics production at LHO
  Design on track
  Procurement late by ~2 months (person power & money & H2 unavailable)

## Slide 9: Plan
Need to get the next review done!
  Funding is now becoming the holdup
Need get some additional resources for
  Electronics production at LHO
  Setup at MIT
  Procurement
ANU will continue on development of OPO
  On track for 2010 delivery
Setup at MIT will continue with SHG & laser locking
Electronics production can go forward for RF, photodetectors, TTFFS and length servos

## Slide 10: Summary
Impressive progress on the OPO
Setup at MIT is coming along
No major roadblocks so far
More funding is needed in a very short time
Some additional person-power is required at MIT and LHO for the second half of this year