## Sheet1
Document #: C1000620-v3
Drawing List for SOW C1000241:
DCC# | rev | Description |  | Total Quantity needed: | Delivered to MIT by 8/27/2010 | Delivered to LHO by 9/20/2010 | Delivered to LLO by 10/25/2010 | Delivered to LHO by 11/19/2010 | Delivered to LLO by 1/3/2011 | Delivered to LHO by 2/14/2011 | Delivered to LLO by 3/28/2011 | Delivered to LHO by 3/28/2011 | Delivered to LHO by 4/18/2011
D047935 | v3 | Spherical Pin | 0-1 AND 1-2 locker | 90 | 6 | 12 | 12 | 12 | 12 | 12 | 6 | 6 | 12
D047942 | v2 | Custom washer | 0-1 AND 1-2 locker | 360 | 24 | 48 | 48 | 48 | 48 | 48 | 24 | 24 | 48
D0901183 | v1 | vert bridge | 0-1 vert. actuator | 45 | 3 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6
D0901554 | v1 | actuator post | 0-1 vert. actuator | 45 | 3 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6
D0901805 | v1 | Stage 0-1 Locker Shims | 0-1 locker | 70 of each type 00 thru 10 | 6 sets | 8 sets | 8 sets | 8 sets | 8 sets | 8 sets | 8 sets | 8 sets | 8 sets
D0902134 | v1 | magnet interposer | 1-2 horizontal actuator | 45 | 3 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6
D0902136 | v1 | tooling bracket | 1-2 horizontal actuator- tooling | 27 | 3 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0
D0902137 | v1 | tooling bracket | 1-2 vert actuator-- tooling | 27 | 3 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0
D0902153 | v1 | thermal bar right | 1-2 vert AND horiz. actuator | 90 | 6 | 12 | 12 | 12 | 12 | 12 | 6 | 6 | 12
D0902154 | v1 | thermal bar left | 1-2 vert AND horiz. actuator | 90 | 6 | 12 | 12 | 12 | 12 | 12 | 6 | 6 | 12
D0902155 | v1 | coil bracket | 1-2 vert actuator | 45 | 3 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6
D0902156 | v1 | spherical washer 2" concave | 1-2 vert AND horiz. actuator | 90 | 6 | 12 | 12 | 12 | 12 | 12 | 6 | 6 | 12
D0902157 | v1 | spherical washer 1" convex | 1-2 vert AND horiz. actuator | 90 | 6 | 12 | 12 | 12 | 12 | 12 | 6 | 6 | 12
D0902161 | v1 | magnet mount | 1-2 vert actuator | 45 | 3 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6
D0902162 | v1 | slide bracket | 1-2 horizontal actuator | 45 | 3 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6
D0902236 | v1 | bracket | 1-2 vert actuator | 45 | 3 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6
D0902249 | v1 | sensor mount | 1-2 vert actuator | 45 | 3 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6
D0902250 | v1 | sensor mount | 1-2 horizontal actuator | 45 | 3 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6
D0902251 | v1 | target mount | 1-2 vert actuator | 45 | 3 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6
D0902252 | v1 | target mount | 1-2 horizontal actuator | 45 | 3 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6
D0902310 | v1 | Magnet bracket | 0-1 vert AND horiz actuator | 90 | 6 | 12 | 12 | 12 | 12 | 12 | 6 | 6 | 12
D0902342 | v1 | tooling bar | 0-1 vert AND horiz actuator- tooling | 54 | 6 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0
D0902356 | v1 | mount | 0-1 vert AND horiz actuator | 90 | 6 | 12 | 12 | 12 | 12 | 12 | 6 | 6 | 12
D0902422 | v1 | right connector | 0-1 vert. actuator | 45 | 3 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6
D0902424 | v1 | connector | 0-1 horiz. Actuator | 90 | 6 | 12 | 12 | 12 | 12 | 12 | 6 | 6 | 12
D0902426 | v1 | vert coil bracket | 0-1 vert. actuator | 45 | 3 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6
D0902427 | v1 | vertical coil bracket | 0-1 vert. Actuator | 45 | 3 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6
D0902428 | v1 | left connector | 0-1 vert. actuator | 45 | 3 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6
D0902435 | v1 | pin carrier | 1-2 vert. AND horiz. actuator-- tooling | 60 | 12 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0
D0902436 | v1 | PIN Carrier | 0-1 vert AND horiz actuator- tooling | 60 | 12 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0
D0902551 | v1 | Stage 1-2 Locker Shims | 1-2 locker | 70 of each type 00 thru 10 | 6 sets | 8 sets | 8 sets | 8 sets | 8 sets | 8 sets | 8 sets | 8 sets | 8 sets
D0902610 | v1 | spherical washer | 0-1 AND 1-2, vert AND horiz actuators | 180 | 12 | 24 | 24 | 24 | 24 | 24 | 12 | 12 | 24
D1000175 | v1 | left thermal bar | 0-1 vert AND horiz actuator | 90 | 6 | 12 | 12 | 12 | 12 | 12 | 6 | 6 | 12
D1000176 | v1 | right thermal bar | 0-1 vert AND horiz actuator | 90 | 6 | 12 | 12 | 12 | 12 | 12 | 6 | 6 | 12
D1000469 | v1 | sensor base | 0-1 AND 1-2, vert AND horiz actuators | 180 | 12 | 24 | 24 | 24 | 24 | 24 | 12 | 12 | 24
D1000470 | v1 | target | 0-1 AND 1-2, vert AND horiz actuators | 180 | 12 | 24 | 24 | 24 | 24 | 24 | 12 | 12 | 24
D1000472 | v1 | target body | 0-1 AND 1-2, vert AND horiz actuators | 180 | 12 | 24 | 24 | 24 | 24 | 24 | 12 | 12 | 24
D1000678 | v1 | spherical washer 2" convex | 1-2 vert AND horiz. actuator | 90 | 6 | 12 | 12 | 12 | 12 | 12 | 6 | 6 | 12
D1000679 | v1 | spherical washer 1" concave | 1-2 vert AND horiz. actuator | 90 | 6 | 12 | 12 | 12 | 12 | 12 | 6 | 6 | 12
D1000860 | v1 | Stage 0-1 Sleeve | 0-1 locker | 45 | 3 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6
D1000861 | v1 | Stage 0-1 Post | 0-1 locker | 45 | 3 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6
D1000862 | v1 | Cap | 0-1 AND 1-2 locker | 180 | 12 | 24 | 24 | 24 | 24 | 24 | 12 | 12 | 24
D1000873 | v1 | Stage 1-2 Post | 1-2 locker | 45 | 3 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6
D1000875 | v1 | Stage 1-2Sleeve | 1-2 locker | 45 | 3 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | 6
D1000908 | v1 | Housing | 0-1 AND 1-2 locker | 90 | 6 | 12 | 12 | 12 | 12 | 12 | 6 | 6 | 12