## Sheet1
Count | 68 |  | 68 | 61 | 60 | 56 | 57 | 42 | 72 |  | 72 | 68 | 63 | 58 | 60 | 45 | 87
% of received |  |  | 100 | 89.7 | 88.2 | 91.8 | 93.4 | 61.7647 |  |  | 100 | 94.4 | 87.5 | 85.3 | 88.2 | 62.5 | 62.1429
Number of ISIs | 22.7 |  | 22.7 | 20.3 | 20 | 18.7 | 19 |  | 24 |  | 24 | 22.7 | 21 | 19.3 | 20 |  | 4.6667
Failure rate (%) |  |  |  | 0 | [7 empty] | 3.2
2014-01-16
E1000136-v15 | Verticals | Location | Received | AR QA | Podded | Pod S/N | Leak Checked | Rework | Horizontals | Location | Received | AR QA | Podded | Pod S/N | Leak Checked | Rework
lho bsc | 798 | high bay | yes | pass | yes | 45 | pass | Yes | 812 | Lab | yes | pass
| 799 | SPSR | yes | pass | yes | 11 | pass |  | 813 | SPSR | yes | pass | yes | 119 | pass | yes
llo_bsc_5 | 800 | L1_BSC5 | yes | pass | yes | 66 | pass | Yes | 814 | SPSR | yes | pass
| 801 | H1_BSC2 | yes | pass | yes | 42 | pass |  | 815 | BSC_LHO1 | yes | pass | yes | X-22 | pass | Waived
| 802 | SPSR | yes | pass | yes | 194/154 | pass |  | 816 | MIT | yes | pass
| 803 | MIT | yes | pass |  |  |  | Waived | 817 | L1_BSC1 | yes | pass | yes | 124 | pass | Yes
| 804 | H1_HAM4 | yes | pass | yes | 14 | pass | Yes | 818 | H1_BSC2 | yes | pass | yes | 53 | pass | yes
| 805 | H1_BSC2 | yes | pass | yes | 91 | pass | Yes | 819 | BSC_LHO3 | yes | pass | yes | 129 | pass
| 806 | LLO | yes | pass | yes | 65 | pass |  | 820 | H1_HAM5 | yes | pass | yes | 89 | pass | yes | ham
| 807 | H1_HAM5 | yes | pass | yes | 73 | pass | yes | 821 | SPSR | yes | pass | yes | 29 | pass | yes
| 808 | L1_HAM4 | yes | pass | yes | 128 | pass | Yes | 822 | L1_BSC3 | yes | pass | yes | 57 | pass | Yes
| 809 | SPSR | yes | pass | yes | 43 | pass | Yes | 823 | H1_BSC3 | yes | pass | yes | 33 | pass
lho | 810 | H1_BSC9 | yes | pass | yes | 48 | pass | Yes | 824 | L1_BSC2 | yes | pass | yes | 5 | pass | Yes
| 811 | BSC_LHO1 | yes | pass | yes | 153 | pass | Waived | 825 | SPSR | yes | pass | yes | 36 | pass | Yes
| 917 | SPSR | yes | pass | y es | 125 |  |  | 945 | L1_BSC4 | yes | pass | yes | 108
| 918 | SPSR | yes | pass | yes | 115 | pass | Yes | 946 | LASTI | yes | pass | yes | X-21 | pass | Waived | ham
| 919 | SPSR | yes | no |  |  |  |  | 947 | LHO | yes | pass | yes | 23 | pass | yes | lho bsc
| 920 | H1_HAM5 | yes | pass | yes | 132 | pass | Yes | 948 | Lab | yes | pass
| 921 | SPSR | yes | pass | yes | 50 | pass | yes | 949 | H1_HAM4 | yes | pass | yes | 90 | pass | yes | ham
| 922 | L1_BSC2 | yes | pass | yes | 49 | pass | Yes | 950 | H1_BSC3 | yes | pass | yes | 68 | pass
lho bsc | 923 | SPSR | yes | pass | yes | 47 | pass | yes | 951 | BSC_LHO3 | yes | pass | yes | 28 | pass
| 924 | SPSR | yes | no |  |  |  |  | 952 | H1_BSC9 | yes | pass | yes | 70 | pass | yes
| 925 | H1_BSC3 | yes | pass | yes | 35 | pass | Yes | 953 | L1_HAM5 | yes | pass | yes | 77 | pass | yes | ham
| 926 | L1_BSC3 | yes | pass | yes | 121 | pass | Yes | 954 | SPSR | yes | pass | yes | 40 | pass | pass
| 927 | High Bay Lab | yes | pass |  |  |  |  | 955 | L1_HAM5 | yes | pass | yes | 141 | pass | yes
| 928 | SPSR | yes | pass | yes | 86 | pass | Yes | 956 | LLO | yes | pass | yes | 71 | pass
| 929 | BSC_LHO2 | yes | pass | yes | 17 | pass | Waived | 957 | L1_BSC5 | yes | pass | yes | 146 | pass | yes | llo_bsc_5
| 930 | H1_BSC9 | yes | pass | yes | 101 |  | Yes | 958 | MIT | yes | pass
| 931 | L1_BSC1 | yes | pass | yes | 78 | pass | Yes | 959 | L1_BSC2 | yes | pass | yes | 10 | pass | Yes
| 932 | LHO | yes | pass | yes | 63 | pass | No | 960 | H1_HAM4 | yes | pass | yes | 114 | pass | yes | ham
| 933 | L1_BSC4 | yes | pass | yes | 140 | pass |  | 961 | H1_BSC1 | yes | pass | yes | 46 | pass | yes
| 934 | SPSR | yes | pass |  |  |  |  | 962 | SPSR | yes | pass | yes | 147 | pass | yes
| 935 | SPSR | yes | pass | yes | 105 |  |  | 963 | LASTI | yes | pass | yes | X-24 | pass | Waived | ham
| 936 | SPSR | yes | pass | yes | 19 | pass | Yes | 964 | SPSR | yes | pass | yes | X-41 | pass
| 937 | LASTI | yes | pass | yes | X-34 |  | Waived? | 965 | L1_BSC5 | yes | pass | yes | 149 | pass | Yes | llo_bsc_5
| 938 | LLO | yes | pass | yes | 69 | pass |  | 966 | L1_BSC3 | yes | pass | yes | 139 | pass | yes
| 939 | LHO | yes | pass | yes | 72 | pass |  | 967 | H1_BSC9 | yes | pass | yes | 137 | pass | Yes | lho
| 940 | High Bay | yes | pass | yes | 87 | pass |  | 968 | BSC_LHO1 | yes | pass | yes | 150 | pass | Waived
| 941 | L1_BSC2 | yes | pass | yes | 13 | pass | Yes | 969 | L1_BSC4 | yes | fail | yes | 12 | pass
lho bsc | 942 | SPSR | yes | pass | yes | 80 | pass | yes | 970 | BSC_LHO2 | yes | pass | yes | 80 | pass | yes | llo
| 943 | L1_HAM4 | yes | pass | yes | 83 | pass | Yes | 971 | SPSR | yes | pass | yes | 136 | pass | yes
| 944 | SPSR | yes | pass | yes | 145 | pass | yes | 972 | LASTI | yes | pass | yes | X-1 | pass | Waived | ham
| 1066 | LLO | yes | pass | yes | 7 | pass |  | 1076 | SPSR | yes | no
| 1067 | LLO | yes | pass | yes | 15 | pass | yes | 1077 | SPSR | yes | pass | yes | 25 | pass | Yes
| 1068 | BSC_LHO1 | yes | pass | yes | 155 | pass | Waived | 1094 | BSC_LHO1 | yes | pass | yes | 152 | pass | Waived
| 1069 | H1_HAM4 | yes | pass | yes | 41 | pass |  | 1095 | H1_BSC3 | yes | pass | yes | 142 | pass
| 1070 | H1_BSC3 | yes | pass | yes | 151 | pass | Waived | 1096 | H1_HAM5 | yes | pass | yes | 134 | pass
| 1071 | LVEA | yes | pass |  |  |  |  | 1097 | L1_BSC1 | yes | pass | yes | 34 | pass | Yes
| 1072 | BSC_LHO2 | yes | pass | yes | X-45 | pass | Waived | 1098 | SPSR | yes | pass | yes | 56 | pass | Yes
| 1073 | H1_BSC9 | yes | pass | yes | 31 | pass |  | 1099 | L1_BSC2 | yes | pass | yes | 98 | pass | Yes
| 1074 | L1_BSC1 | yes | pass | yes | 32 | pass | Yes | 1100 | L1_BSC4 | yes | fail | yes | 84 |  |  | lho
| 1075 | L1_BSC4 | yes | pass | yes | 59 | pass | Yes | 1101 | H1_HAM5 | yes | pass | yes | 60 | pass | yes
| 1078 | H1_BSC2 | yes | pass | yes | 62 | pass | Yes | 1102 | L1_HAM4 | yes | pass | yes | 82 | pass | yes
| 1079 | LHO | yes | pass | yes | 39 | pass | no | 1103 | L1_HAM4 | yes | pass | yes | 100 | pass | yes | ham
| 1080 | H1_BSC3 | yes | pass | yes | 85 | pass |  | 1104 | H1_BSC1 | yes | pass | yes | 96 | pass |  | ham
| 1081 | L1_BSC3 | yes | no | yes | 118 | pass | Yes | 1105 | BSC_LHO3 | yes | pass | yes | 76 | pass |  | ham
| 1082 | L1_BSC3 | yes | pass | yes | 144 | pass | Yes | 1106 | L1_BSC2 | yes | pass | yes | 51 | pass | Yes
| 1083 | H1_HAM4 | yes | pass | yes | 52 | pass |  | 1107 | Lab | yes | pass
| 1084 | L1_BSC1 | yes | pass | yes | 138 | pass | Yes | 1108 | L1_HAM5 | yes | pass | yes | 55 | pass | yes | llo_bsc_5
| 1085 | BSC_LHO2 | yes | no | yes | 37 | pass | Waived | 1109 | SPSR | yes | pass | yes | 27 | pass | Yes | ham
| 1086 | L1_BSC5 | yes | pass | yes | 61 | pass |  | 1110 | L1_HAM4 | yes | pass | yes | 88 | pass | yes | lho
| 1087 | SPSR | yes | pass |  |  |  |  | 1111 | L1_BSC3 | yes | pass | yes | 2 | pass | Yes | ham
| 1088 | L1_BSC4 | yes | no | yes | 95 | pass |  | 1112 | MIT | yes | pass
| 1089 | BSC_LHO1 | yes | pass | yes | 127 | pass | Waived | 1113 | SPSR | yes | pass | yes | 92
llo_bsc_5 | 1090 | LASTI | yes | no | yes | X-26 | pass | Waived | 1114 | LHO | yes | pass | yes | 24 | pass | yes
| 1091 | SPSR | yes | pass | yes | X-15 | pass |  | 1115 | H1_BSC9 | yes | pass | yes | 79 | pass | Yes | lho bsc
| 1092 | L1_BSC5 | yes | pass | yes | 16 | pass | Yes | 1116 | SPSR | yes | pass | yes | 58 | pass | yes | lho
| 1093 | SPSR | yes | no | yes | 18 | pass | Yes | 1117 | L1_BSC5 | yes | fail | yes | 54 | pass | Yes | lho bsc
| 1611 | SPSR | yes |  | yes | HEPI |  |  | 1118 | Lab | yes | pass |  |  |  |  | llo_bsc_5
| 1612 | SPSR | yes |  |  |  |  | yes | 1119 | H1_HAM4 | yes | pass | yes | 6 | pass | Yes
| 1613 | SPSR | yes | [5 empty] | 1120 | H1_BSC1 | yes | pass | yes | 94 | pass |  | ham
| 1614 | SPSR | yes |  | yes | HEPI |  |  | 1121 | SPSR | yes | pass | yes | 44 | pass | Yes
| 1615 | SPSR | yes |  | yes | HEPI |  |  | 1652 | SPSR | yes | [5 empty] | lho
| 1616 | SPSR | yes | [5 empty] | 1653 | SPSR | yes |  | yes | HEPI
| 1618 | SPSR | yes |  | yes | HEPI |  |  | 1654 | SPSR | yes |  | yes | HEPI
| 1619 | SPSR | yes | [5 empty] | 1656 | SPSR | yes
| 1620 | SPSR | yes | [5 empty] | 1657 | SPSR | yes
| 1621 | SPSR | yes | [5 empty] | 1658 | SPSR | yes
| 1623 | SPSR | yes | [5 empty] | 1660 | SPSR | yes
| 1624 | SPSR | yes |  | yes | HEPI |  |  | 1661 | SPSR | yes
| 1625 | SPSR | yes | [5 empty] | 1663 | SPSR | yes |  | yes | HEPI
| 1626 | SPSR | yes | [5 empty] | 1664 | SPSR | yes |  | yes | HEPI
| 1627 | LVEA | yes |  | yes | HEPI |  |  | 1666 | SPSR | yes |  | yes | HEPI
| 1628 | SPSR | yes | [5 empty] | 1667 | SPSR | yes
| 1629 | SPSR | yes |  | yes | HEPI |  |  | 1668 | SPSR | yes
| 1630 | SPSR | yes | [5 empty] | 1669 | SPSR | yes |  | yes | HEPI
| 1631 | SPSR | yes | [5 empty] | 1670 | SPSR | yes
| 1632 | SPSR | yes | [5 empty] | 1671 | SPSR | yes
| 1633 | SPSR | yes | [5 empty] | 1672 | SPSR | yes
| 1634 | SPSR | yes |  | yes | HEPI |  |  | 1673 | SPSR | yes
| 1635 | SPSR | yes | [5 empty] | 1674 | SPSR | yes
| 1636 | SPSR | yes | [5 empty] | 1675 | SPSR | yes |  | yes | HEPI
| 1637 | SPSR | yes |  | yes | HEPI |  |  | 1676 | SPSR | yes |  | yes | HEPI
| 1638 | SPSR | yes | [5 empty] | 1677 | SPSR | yes |  | yes | HEPI
| 1639 | SPSR | yes | [5 empty] | 1678 | SPSR | yes
| 1640 | SPSR | yes | [5 empty] | 1679 | SPSR | yes
| 1641 | SPSR | yes | [5 empty] | 1680 | SPSR | yes
| 1642 | SPSR | yes | [5 empty] | 1681 | SPSR | yes
| 1643 | SPSR | yes | [5 empty] | 1682 | SPSR | yes |  | yes | HEPI
| 1644 | SPSR | yes | [5 empty] | 1683 | SPSR | yes
| 1645 | SPSR | yes | [5 empty] | 1684 | SPSR | yes |  | yes | HEPI
| 1646 | SPSR | yes | [5 empty] | 1685 | SPSR | yes
| 1647 | SPSR | yes | [5 empty] | 1686 | SPSR | yes
| 1648 | SPSR | yes | [5 empty] | 1687 | SPSR | yes
| 1649 | SPSR | yes | [5 empty] | 1688 | SPSR | yes
| 1650 | SPSR | yes | [5 empty] | 1689 | SPSR | yes
| 1651 | SPSR | yes | [5 empty] | 1690 | SPSR | yes |  | yes | HEPI
| 929 | L1_BSC2 | yes | pass | yes | 103 | pass |  | 1691 | SPSR | yes
[9 empty] | 1692 | SPSR | yes
[9 empty] | 1693 | SPSR | yes
[8 empty] | yes | 1694 | SPSR | yes