## E1100730-v4
E1100730 | -v4 |  | HAM and BSC SEI In-Vacuum Cabling Counts including payload cables as well as BSC SLC ACB and BSC TCS
DCC Number | GROUP | Description | Length (in.) | Qty requested | qty received | missing | LLO HAM1 | LLO HAM2 | LLO HAM3 | LLO HAM4 | LLO HAM5 | LLO HAM6 | LHO HAM1 | LHO HAM2 | LHO HAM3 | LHO HAM4 | LHO HAM5 | LHO HAM6 | LHO HAM7 | LHO HAM8 | LHO HAM9 | LHO HAM10 | LHO HAM11 | LHO HAM12 | QTY Needed Total | Qty Needed through HAM 5 |  | Qty requested | Shortfall 2011? | Shortfall 2012? | DCC Number
HAM Cables | [30 empty] | HAM Cables
D1000220 | SEI | 25-pin F-to-25-pin F | 40 | 26 | 27 | -1 |  | 1 | 1 | 2 | 2 | 1 |  | 1 | 1 | 2 | 2 |  |  | 1 | 1 | 2 | 2 |  | 19 | 6 |  | 27 | -21 | -8 | D1000220
D1000221 | SEI | 25-pin F-to-25-pin F | 100 | 26 | 27 | -1 |  | 1 | 1 | 2 | 2 | 1 |  | 1 | 1 | 2 | 2 |  |  | 1 | 1 | 2 | 2 |  | 19 | 6 |  | 27 | -21 | -8 | D1000221
D1000222 | SEI | 25-pin F-to-25-pin F | 120 | 26 | 27 | -1 |  | 1 | 1 | 2 | 2 | 1 |  | 1 | 1 | 2 | 2 |  |  | 1 | 1 | 2 | 2 |  | 19 | 6 |  | 27 | -21 | -8 | D1000222
D1000225 (108") | SEI (Payload) | 25-pin F-to-25-pin F | 108 | 38 | 38 | 0 |  | 18 | 9 | 5 | 6 |  |  | 18 | 9 | 5 | 5 |  |  | 18 | 6 | 5 | 5 |  | 109 | 38 |  | 38 | 0 | 71 | D1000225 (108")
D1000225 (180") | SEI (Payload) | 25-pin F-to-25-pin F | 180 | 105 |  | 105 | 10 | 8 | 2 |  | 3 | 16 | 10 | 8 | 2 |  | 4 | 16 | 10 | 8 | 5 |  | 4 | 16 | 106 | 13 |  | 105 | -92 | 1 | D1000225 (180")
D1000225 (199") | SEI (Payload) | 25-pin F-to-25-pin F | 199 | 7 | 7 | 0 | [18 empty] | 0 | 0 |  | 7 | -7 | -7 | D1000225 (199")
D1000225 (209") | SEI (Payload) | 25-pin F-to-25-pin F | 209 | 22 | 22 | 0 | [18 empty] | 0 | 0 |  | 22 | -22 | -22 | D1000225 (209")
D1000225 (230") | SEI (Payload) | 25-pin F-to-25-pin F | 230 | 40 | 40 | 0 | [18 empty] | 0 | 0 |  | 40 | -40 | -40 | D1000225 (230")
D1000227 | SEI | 25-pin M-to-one 9-pin F straight, one 9-pinF R/A | 36 | 73 | 66 | 7 |  | 3 | 3 | 6 | 6 | 3 |  | 3 | 3 | 6 | 6 |  |  | 3 | 3 | 6 | 6 |  | 57 | 18 |  | 73 | -55 | -16 | D1000227
D1000218 | SEI | 2-wire, 14awg 2 pins to 3-pin F | 25 | 21 | 21 | 0 |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 |  | 13 | 4 |  | 21 | -17 | -8 | D1000218
D1000918 | SEI | 2-wire, 14awg 2 pins to 3-pin F | 70 | 36 | 36 | 0 |  | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 |  | 26 | 8 |  | 36 | -28 | -10 | D1000918
D1000919 | SEI | 2-wire, 14awg 2 pins to 3-pin F | 95 | 36 | 36 | 0 |  | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 |  | 26 | 8 |  | 36 | -28 | -10 | D1000919
D1000920 | SEI | 2-wire, 14awg 2 pins to 3-pin F | 135 | 21 | 21 | 0 |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 |  | 13 | 4 |  | 21 | -17 | -8 | D1000920
D1000225 (230") | PSL | Payload cable | 230 | ordered?
D1000220 (40") | PSL | Component cable | 40 | ordered?
| IO | HAM Aux |  | status?
| IO | IO QPD component cables |  | status?
| IO / ISC | Pico-motor component cables |  | status?
| ISC | HAM1/6 and HAM7/12 component cables |  | status?
D1000234 (60") | SUS | DB25 to uDB9 quadra-puss | 60 | 53 | 53 |  |  | 4 | 5 | 1 | 1 | 0 | 4 | 5 | 1 | 1 | 0 |  |  | 9 | 3 | 2 | 2 |  | 38 | 11
D1000234 (66") | SUS | DB25 to uDB9 quadra-puss | 66 | 26 | 26 |  |  | 3 | 1 | 3 | 3 | 0 | 3 | 1 | 3 | 3 | 0 |  |  | 3 | 1 | 2 | 0 |  | 26 | 10
D1000234 (78") | SUS | DB25 to uDB9 quadra-puss | 78 | 15 | 15 |  |  | 5 | 0 | 0 | 2 | 0 | 5 | 0 | 0 | 2 | 0 |  |  | 1 | 1 | 0 | 4 |  | 20 | 7
D1000234 (88") | SUS | DB25 to uDB9 quadra-puss | 88 | 44 | 44 |  |  | 2 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 1 | 0 |  |  | 0 | 2 | 0 | 1 |  | 9 | 3
D1000234 (96") | SUS | DB25 to uDB9 quadra-puss | 96 | 15 | 15 |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  |  | 1 | 0 | 0 | 0 |  | 3 | 1
BSC Cables |  |  |  | Total | Delivery for S.A. | missing | LLO BSC1 | LLO BSC2 | LLO BSC3 | LLO BSC4 | LLO BSC5 | LHOBSC1 | LHOBSC2 | LHOBSC3 | LHOBSC4 | LHOBSC5 | LHOBSC6 | LHOBSC7 | LHOBSC8 | LHOBSC9 | LHOBSC10 |  |  |  |  | Qty Single Arm | Req. for Single Arm | Total |  |  | BSC Cables
D1100148 | SEI | 2-wire, 14awg 3-pin M to 3-pin F | 80 | 204 |  | 204 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  |  |  | 180 | 24 | 25 | 204 |  | -24 | D1100148
D1100150 | SEI | 2-wire, 14awg 2 pins to 3-pin F | 40 | 102 | 13 | 89 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 |  |  |  | 90 | 12 | 13 | 102 |  | -12 | D1100150
D1100151 | SEI | 2-wire, 14awg 2 pins to 3-pin F | 60 | 102 | 13 | 89 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 |  |  |  | 90 | 12 | 13 | 102 |  | -12 | D1100151
D1100152 | SEI | 25-pin F-to-25-pin F | 110 | 51 | 7 | 44 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  | 45 | 6 | 7 | 51 |  | -6 | D1100152
D1100153 | SEI | 25-pin F-to-25-pin F | 80 | 204 | 25 | 179 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  |  |  | 180 | 24 | 25 | 204 |  | -24 | D1100153
D1100154 | SEI | 25-pin M-to-two 9-pin F straight | 48 | 102 | 13 | 89 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 |  |  |  | 90 | 12 | 13 | 102 |  | -12 | D1100154
D1100155 | SEI | 25-pin M-to-two 9-pin F straight | 120 | 102 | 13 | 89 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 |  |  |  | 90 | 12 | 13 | 102 |  | -12 | D1100155
D1000225 (180") | SEI (Payload) | 25-pin F-to-25-pin F | 180 |  |  |  | 7 |  | 6 |  | 11 | 6 |  | 6 |  | 2 | 6 | 5 | 7 |  | 12 |  |  |  | 68 | 13 |  |  | -15 | 58 | D1000225 (180")
D1000225 (199") | SEI (Payload) | 25-pin F-to-25-pin F | 199 | 7 | [6 empty] | 2 | LHOBSC4: 3; LHOBSC6: 2; LHOBSC8: 3; LHOBSC9: 2; LHOBSC10: 2 |  |  |  | 14 | 5 |  | 7 | -12 | 6 | D1000225 (199")
D1000225 (209") | SEI (Payload) | 25-pin F-to-25-pin F | 209 | 22 |  |  | 2 | 3 | 1 | 2 |  | LHOBSC1: 2; LHOBSC2: 3; LHOBSC3: 2; LHOBSC5: 12; LHOBSC7: 7 |  |  |  | 34 | 0 |  | 22 | 0 | 34 | D1000225 (209")
D1000225 (230") | SEI (Payload) | 25-pin F-to-25-pin F | 230 | 40 |  |  |  |  | 1 | 13 | 2 | LHOBSC6: 6; LHOBSC8: 2; LHOBSC9: 14; LHOBSC10: 2 |  |  |  | 40 | 8 |  | 40 | 8 | 40 | D1000225 (230")
D1001517-v5 | TCS | TCS Ring Heater In-Vac Cable Assembly | 196 | in house |  |  | 1 |  | 1 | 1 | 1 | [13 empty] | 12 | bar: LHOBSC1; LHOBSC3; LHOBSC5 to LHOBSC10
D1003111 | AOS | SLC PHOTODETECTOR CABLE LOWER ASSY | 69 | in house |  |  | 1 |  | 1 | 1 | 1 | LHOBSC7: 2; LHOBSC8: 2; LHOBSC9: 2; LHOBSC10: 2 |  |  |  | 12
D1003117-1 | AOS | SLC PHOTODETECTOR CABLE UPPER ASSY | 175 | in house |  |  | 1 |  |  |  | 1 | LHOBSC7: 2; LHOBSC10: 2 |  |  |  | 6
D1003117-2 | AOS | SLC PHOTODETECTOR CABLE UPPER ASSY | 241 | in house |  |  |  |  | 1 | 1 |  | LHOBSC8: 2; LHOBSC9: 2 |  |  |  | 6
DCC Number |  | Description |  |  |  |  | LLO BSC1 | LLO BSC2 | LLO BSC3 | LLO BSC4 | LLO BSC5 | LHOBSC1 | LHOBSC2 | LHOBSC3 | LHOBSC4 | LHOBSC5 | LHOBSC6 | LHOBSC7 | LHOBSC8 | LHOBSC9 | LHOBSC10
[7 empty] | ITMY | BS | ITMX | ETMX/TMS | ETMY/TMS | ITMY | BS | ITMX | BS | ETMX/TMS | ETMY/TMS | ITMX/FMY | ITMY/FMY | ETMX/TMS | ETMY/TMS
D1000234 (88") | SUS | DB25 to uDB9 quadra-puss | 88 | 44 |  |  | 3 |  | 3 | 3 | 3 | 3 |  | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  | 36
D1000234 (96") | TMS | DB25 to uDB9 quadra-puss | 96 | 15 | [5 empty] | 2 | 2 | LHOBSC5: 2; LHOBSC6: 2; 2 LHOBSC9: 2; 2 LHOBSC10: 2 |  |  |  | 12
D1000234 (125") | SUS | DB25 to uDB9 quadra-puss | 125 | 20 |  |  |  | 3 |  |  |  | LHOBSC2: 3; LHOBSC4: 3; LHOBSC7: 3; 2 LHOBSC8: 3 |  |  |  | 15
D1002522 (110") | SUS | DB25 to DB25 single cable | 110 | 10 |  |  | 1 |  | 1 | [15 empty] | 7 | bar: LHOBSC1; LHOBSC3; LHOBSC7; 2 LHOBSC9 to 2 LHOBSC10
D1002522 (121") | SUS | DB25 to DB25 single cable | 121 | [6 empty] | 1 | 1 | [13 empty] | 4 | bar: LHOBSC6; 2 LHOBSC8
D1002522 (156") | SUS | DB25 to DB25 single cable | 156 |  |  |  | 1 |  | 1 | 1 | 1 | 1 |  | 1 |  | 2 | 1 | 1 | 1 | 1 | 1 |  |  |  | 13
D1002523 | SUS | uDB25 to uDB9 quadra-puss | ? |  |  |  | 1 |  | 1 | 1 | 1 | [13 empty] | 12 | bar: LHOBSC1; LHOBSC3; LHOBSC5 to 2 LHOBSC10
D1002524 | SUS | uDB25 to uDB9 quadra-puss |  |  |  |  | 1 |  | 1 | 1 | 1 | [13 empty] | 12 | bar: LHOBSC1; LHOBSC3; LHOBSC5 to 2 LHOBSC10
D1101472 | SUS | ESD
Pass Test and are Class A
|  | Schedule of need |  |  |  |  | LHO BSC8 | August
[7 empty] | LHO BSC6 | Late August
[7 empty] | LLO HAM3 | September
[7 empty] | LLO HAM2 | October
[7 empty] | LLO HAM4 | November
[7 empty] | LLO HAM5 | December
[7 empty] | LLO BSC2 | December

## VacCableProcurements
Jay's SUS orders - All cables received
|  | DB25 to 4xuDB9 | [6 empty] | Extension Cables DB25 to uDB25 |  |  |  |  | uDB25 to 4xuDB9
PO # | Date | D1000234-53 | D1000234v2-60 | D1000234v2-66 | D1000234v2-78 | D1000234v2-88 | D1000234v2-96 | D1000234v2-125 | D1002522-150 | D1002522-115 | D1002522-110 | D1002521-90 | D1000566-53 | D1002523-12 | D1002523-17
S119307 | 2011-06-24 | 0 | 40 | 12 | 5 | 2 | 0 | 10 | 0 | 0 |  |  |  | 0 | 0
S118679 | 2011-06-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 6 | 6
S111649 | 2011-03-04 | 0 | 9 | 14 | 10 | 42 | 15 | 10 | 0 | 0 |  |  |  | 0 | 0
S109883 | 2011-02-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 5 |  |  |  | 0 | 0
S103886 | 2010-11-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 |  | 0 | 0
S102106 | 2010-10-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10 | 10
S099727 | 2010-09-02 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0
S094191 | 2010-06-15 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | other cables in order are unuseable
TOTALS |  | 24 | 53 | 26 | 15 | 44 | 15 | 20 | 19 | 5 | 10 | 10 | 4 | 16 | 16
[16 empty] | 277 | TOTAL # Cabls