## Sheet1
Column1 | Column2
Tests of E100309 | Rule / Comments
I. Pre-Assembly Testing 6
§ Step 1 - Position Sensors | Update to reflect the changes made since the Assembly Validation
§ Step 2 - GS13 - E1000058 – E1200081 – Testing prior to shipping | Update to reflect the changes made since the Assembly Validation
§ Step 3 - L4C - E1000058 – E1200081 | Update to reflect the changes made since the Assembly Validation
§ Step 4 - Actuators – E1000136 8 | Update to reflect the changes made since the Assembly Validation
§ Step 5 - Seismometer inspection after shipping | Update to reflect the changes made since the Assembly Validation
II. Tests to be performed during assembly
§ Step 1 - Parts Inventory (E1000052) | Update to reflect the changes made since the Assembly Validation
§ Step 2 - Check torques on all bolts | If walls were opened
§ Step 3 - Check gaps under Support Posts | Waive
§ Step 4 - Pitchfork/Boxwork flatness before Optical Table install | Waive
§ Step 5 - Blade spring profile | Perform
§ Step 6 - Gap checks on actuators-after installation on Stage 1 | Perform
§ Step 7 - Check level of Stage 0 | Waive
§ Step 8 - Check level of Stage 1 Optical Table | Perform
§ Step 9 - Mass budget | Perform
§ Step 10 - Shim thickness | Perform
§ Step 11 - Lockers adjustment | Waive unless step III.4 is too far from requirements
III. Tests to be performed after assembly
§ Step 0.1 - Testing folder set up | Perform
§ Step 0.2 - MEDM set-up for testing | Perform
§ Step 1 - Electronics Inventory | Perform
§ Step 2 - Set up sensors gap | Waive unless the absolute value of CPS readouts is higher than 400cts
§ Step 3 - Measure the gaps on the CPSs | Waived to avoid scratching Targets
§ Step 4 - Check Sensor gaps after the platform release | Defines if step II.11 is needed
§ Step 5 – Performance of the limiter | Performed with drive in step III.10 - Range Of Motion
§ Step 5.1 - Test Nº1 - Push “in the general coordinates” | Performed with drive in step III.10 - Range Of Motion
§ Step 5.2 - Test Nº2 – Push “locally” | Performed with drive in step III.10 - Range Of Motion
§ Step 6 - Position Sensors unlocked/locked Power Spectrum | Perform
§ Step 7 - GS13 power spectrum -tabled tilted | Perform
§ Step 8 - GS13 pressure readout | Perform
§ Step 9 - Coil Driver, cabling and resistance check | Perform
§ Step 10 - Actuators Sign and range of motion (Local drive) | Perform
§ Step 11 - Vertical Sensor Calibration | Waive unless a vertical CPS was changed
§ Step 12 - Vertical Spring Constant | Waive unless (a) blade(s) was(ere) changed.
§ Step 13 - Static Testing (Tests in the local basis) | Perform
§ Step 14 - Linearity test | Perform
§ Step 15 - Cartesian Basis Static Testing | Perform
§ Step 16.1 - Local to local TF measurement | Perform
§ Step 16.2 - GS13 Response Extraction | Perform
§ Step 16.3 - GS13 Response Fitting | Waive unless extra time is available, or concerns arose
§ Step 16.4 - Symmetrization Filters | Waive unless extra time is available, or concerns arose
§ Step 16.5 - Cartesian to Cartesian TF Computation | Waive unless extra time is available, or concerns arose
§ Step 17.1 - Local to local - Comparison with Reference | Waive unless extra time is available, or concerns arose
§ Step 17.2 - Cartesian to Cartesian - Comparison with Reference | Waive unless extra time is available, or concerns arose
§ Step 18 - Lower Zero Moment Plane | Waive unless extra time is available, or concerns arose
§ Step 19 - Damping loops | Waive unless extra time is available, or concerns arose
§ Step 19.1 - Simulation of damping performance - TF | Waive unless extra time is available, or concerns arose
§ Step 19.2 - Experimental evaluation of damping performance - Spectra | Waive unless extra time is available, or concerns arose