## Sheet1
PSL ACCEPTANCE DOCUMENTATION REVIEW |  |  | comments by review team on document E1200039-v3
per M1100282
| acceptance document | document link/reference | status/comments
| Documentation Tree Root DCC entry | E1200038 | OK
Common Documents
| DRD | T050036-v4 | OK
| Final Design Document (FDD) | T0900649-v4 | OK
| final design report | L1000084-v2 | OK
| supporting analyses/models | listed in Table in E1200039-v2 | OK
prototype tests
| drawing/document tree/list | listed in Table in E1200039-v2 | OK
| parts list (BOM) | listed in Table in E1200039-v2 | complete (except for fasteners) -- OK
| spares list | see section 4 of E1200039-v2 | OK
| design drawings, schematics, interfaces, etc. | listed in Table in E1200039-v2 | OK
| SW Vault files | Inventor source files are filed with the pdf mechanical drawings in the DCC | OK
| Electronics Vault Files | Eagle source files are filed with the electronics schedmatic drawings in the DCC | OK
| Front-end or Embedded Software SVN | filed in SVN | OK
| Specifications | C1002229-v1 for LAE Cleanroom | OK
T0900610-v3, PSL table layout drawing has list of components
measured optics reflectances, transmissions
| Assembly procedure(s) | Assembly procedures for the larger sub-assemblies like the high power laser, 35W front-end laser, DBB are available from LZH, neoLASE or AEI | this is acceptable
|  | T1000430, "PMC Construction Manual" is missing from DCC | OK
| Installation plan/procedure(s) | T0900568-v2 | OK
| Test & Commissioning Doc Tree | E1000443 | OK
| Test plan/procedure(s) | listed in section 6 of E1200039-v2 | OK
| User Interface Software SVN | T0900634-v2 | MEDM and scripts filed in SVN - OK
| User's Manual(s) | listed in Table in E1200039-v2 | OK
| Troubleshooting Guide | troubleshooting envisioned at time of design are included in user's manuals; updates based on experience with as-built units is pending | OK
| Safety Docs | T0900614-v1, aLIGO PSL Safety Plan | OK
|  | T1000005-v2, aLIGO PSL Interlock Concept | OK
|  | T1000160-v4, aLIGO PSL Hazards Analysis | OK
|  | M1100258-v1, Procedure to Transition PSL LAE and Diode Room to Laser Safe/Hazard | OK
PSL #1 Documents:
| acceptance document | E1200039 | OK
| ICS inventory | check ICS for US components | German components to be added to ICS after LIGO acceptance & title transfer - pending
| S-numbers | some s-numbers listed in section 6 of E1200039 | OK
| Test results | E1100716-v2 | see pending actions listed in section 5 of E1100716
| Channel/Signal List and Calibrations | TBD | new requirement to be added to M1100282-v2