## summary
FABRICATION ACCEPTANCE REVIEW STATUS
Subsys | Pending | Underway | Completed | Total
AOS | 4 | 10 | 1 | 15
COC | 1 | 0 | 0 | 1
DAQ | 0 | 0 | 1 | 1
DCS | 1 | 0 | 0 | 1
FMP | 0 | 0 | 3 | 3
IO | 0 | 3 | 6 | 9
ISC | 10 | 4 | 2 | 16
PSL | 0 | 2 | 1 | 3
SEI | 46 | 15 | 0 | 61
SUS | 0 | 6 | 44 | 50
Totals | 62 | 40 | 58 | 160
| 38.75% | 25% | 36.25%

## Subsystems
aLIGO Fabrication Acceptance Review Tracking | [6 empty] | G1300115-v11 |  |  |  |  | SCHEDULE WAS NOT UPDATED FOR -V13
|  |  |  | Review Content | [7 empty] | Schedule |  |  | Review Committee
| Pending, Underway, or Completed | Accepted | Punch List Closed | Subsystem | Subassembly | Instance | Acceptance Report (template E1300457) | Acceptance Review Report | Punch List | Lead | Comments/Status | Docs Prepared | Accepted/ Punch List Created | Punch list completed | Chair | [6 empty] | Safety | PM Rep.
| P |  |  | SYS | SYS | L1 |  |  |  |  | acceptance completion from schedule G1000061-v47. Final documents for system testing set 4 wks earlier | 2014-10-08 | 2014-11-05 | TBD | [7 empty] | D. Nolting | M. Levine
| P |  |  | SYS | SYS | H1 |  |  |  |  | acceptance completion from schedule G1000061-v47. Final documents for system testing set 4 wks earlier | 2014-11-12 | 2014-12-10 | TBD
| X |  |  | SYS | [5 empty] | D. Coyne | basic content listed, link structure TBD. Common documents are expected to be all (or mostly) posted, as well as some early system test reports, sufficient to start the review by 3/1/2014. All of the documents, including systems testing results will not be completed until the dates shown for L1 and H1 above. | sufficient to start the review by 3/1/2014 | 2014-12-10 | TBD | F. Raab | J. Giaime | E. Gustafson | Stefan Balmer | M. Landry | B. O'Reilly | Josh Smith | D. Nolting | M. Levine
| P |  |  | AOS - Video System |  |  | T1200556 |  |  | J. Betzwieser |  | date? | date? | TBD | S. Anderson | R. Adhikari | [5 empty] | D. Nolting | M. Levine
| U |  |  | AOS - IAS |  | NA | E1300547 | E1300425 |  | D. Cook | Document is ~90% complete; review starting; to complete in ~6 wks |  | 2013-12-15 | TBD | C. Guido | J. Hanson | C. Vorvick | G. Moreno |  |  |  | D. Nolting | M. Levine
| U |  |  | AOS - OpLev |  |  | E1200026 | T1400232 | L1300227 | E. Gustafson | punch list is very long, but has many installation issues/tasks beyond the Fab Accept Rev scope | done | 12/1/2013 or sooner | TBD | D. Cook | G. Moreno | J. Kissel | C. Vorvick |  |  |  | D. Nolting | M. Levine
| U |  |  | AOS - PCal |  |  | TBD |  |  | R. Savage | all dwgs & BOMs, procedures by 12/31/2013; All documentation (with the possible exception of electronics, software and Operation Manual) by 1/15/2014 Also beam localization system will not be included. | 2014-01-15 | 2014-02-15 | TBD | K. Kawabe | V. Frolov | B. Anderson | J. Lewis |  |  |  | D. Nolting | M. Levine
| U |  |  | AOS - SLC & VP |  |  | E1300212 | T1400233 | E1300806 | M. Smith |  | done | date? | TBD | R. Schofield | J. Lewis | A. Brooks |  |  |  |  | D. Nolting | M. Levine
| U |  |  | AOS - TCS | RH | L1, H1, I1 | E1300799 | T1400004 |  |  |  | 2013-11-30 | 2014-02-01 | TBD
| U |  |  | AOS - TCS | HWS | L1, H1, I1 | E1300802 | T1400005 |  |  |  | 2013-11-30 | 2013-03-01 | TBD
| P |  |  | AOS - TCS | CO2P | L1, H1, I1 | E1200639 | T1400006 |  |  |  | 2013-11-30 | 2013-03-01 | TBD
| X |  |  | AOS - TCS |  |  | E1200636 |  |  | M. Jacobson | RH, HWS docs close to done; CO2P not started, but will be completed by end of Nov | 2013-11-30 | 2014-02-01 | TBD | E. Gustafson | J. Betzwieser | R. Savage | David Tanner |  |  |  | D. Nolting | M. Levine
| U |  |  | AOS - TMS |  | L1 EndX | E1300362 |  |  |  |  | date? | date? | TBD
| U |  |  | AOS - TMS |  | L1 EndY | E1300363 |  |  |  |  | date? | date? | TBD
| U |  |  | AOS - TMS |  | H1 EndX | E1300361 |  |  |  |  | date? | date? | TBD
| U |  |  | AOS - TMS |  | H1 EndY | E1300360 |  |  |  |  | date? | date? | TBD
| P |  |  | AOS - TMS |  | I1 EndX | TBD |  |  |  |  | date? | date? | TBD
| P |  |  | AOS - TMS |  | I1 EndY | TBD |  |  |  |  | date? | date? | TBD
| C |  |  | AOS - TMS |  |  | E1300359 | L1300225 | L1300226 | C. Torrie & E. Gustafson | common document has been mostly completed; documents for individual TMS pending | date? | date? | TBD | F. Matichard | C. Torrie | C. Ramet | L. Barsotti | R. Mittleman | B. Abbott |  | D. Nolting | M. Levine
| P |  |  | COC | COC | L1, H1, I1 |  |  |  | G. Billingsley | Started working on completing the template doc | 2014-01-15 | 2014-03-01 | TBD | P. Fritschel | E. Gustafson | R. Martin |  |  |  |  | D. Nolting | M. Levine
| C |  |  | DAQ | DAQ | L1, H1 | E1300539 | E1300536 |  | R. Bork | ~200 documents; ~95% reviewed; expect acceptance mid-Nov 2013 | done | 2013-11-15 | 2014-02-01 | D. Barker | K. Thorne | R. Mittleman | M. Barton | J. Batch | M. Thomas | V. Sandberg | D. Nolting | M. Levine
| P |  |  | DCS | [5 empty] | S. Anderson |  | 2015-01-31 | 2015-01-31 | 2015-03-23 | V. Sandberg | K. Thorne | R. Bork | A. Weinstein | J. Rollins |  |  | D. Nolting | M. Levine
| C |  |  | FMP | Facility Modifications | L1, H1 | E1300450 | T1300707 |  | J. Worden | L1 documentation has proved a challenge. Checking docs on high value contracts | done | 2013-11-08 | 2014-05-01
| C |  |  | FMP | Tooling | L1, H1, I1 | E1300451 | T1300707 |  | J. Worden | Going slowly: in some cases, FMP just paid the bill. I'm still looking for a few documents. | done | 2013-11-08 | 2014-01-31
| C |  |  | FMP | Software | L1, H1 | E1300452 | T1300707 |  | J. Worden | Completed documents under review | done | 2013-11-08 | 2013-11-30
| X |  |  | FMP |  |  | E1300460 |  |  | J. Worden |  | done | 2013-11-08 | 2014-05-01 | J. Lewis | C. Gray | J. Fauver |  |  |  |  | D. Nolting | M. Levine
| C |  |  | IO | IO on PSL Table | L1, H1, I1 | T1300019 | T1300607 | T1300607 | G. Mueller |  | done | done | TBD
| U |  |  | IO | IO in HAM2 | L1, H1, I1 | T1300021 | T1300897 | T1300897 | G. Mueller |  | 2013-12-31 | 2014-03-01 | TBD
| C |  |  | IO | IO in HAM3 | L1, H1, I1 | T1300022 | T1300896 | T1300896 | G. Mueller | cleaning up some documentation before goes for initial review | 2013-12-01 | 2014-02-01 | TBD
| C |  |  | IO | IO Tables | L1, H1, I1 | T1300023 | T1300900 | T1300900 | G. Mueller |  | 2013-12-31 | 2014-03-01 | TBD
| U |  |  | IO | HAM Aux Sus | L1, H1, I1 | T1300020 | T1300680 | T1300680 | G. Mueller | on hold with reviewers whilst waiting for some documentation to be fixed | 2013-12-01 | 2014-02-01 | TBD
| C |  |  | IO | EOM | L1, H1, I1 | T1300608 | T1300608 | T1300608 | G. Mueller | just sent out for review by reviewers | done | 2014-02-01 | TBD
| U |  |  | IO | Power Control | L1, H1, I1 | T1300089 | T1300898 | T1300898 | G. Mueller |  | 2013-12-31 | 2014-03-01 | TBD
| C |  |  | IO | IMC | L1, H1, I1 | T1300090 | T1300899 | T1300899 | G. Mueller |  | 2013-12-31 | 2014-03-01 | TBD
| C |  |  | IO | IFI | L1, H1, I1 | T1300091 | T1300605 | T1300605 | G. Mueller | What about the I1 unit -- is this covered in the review? | done | done | TBD
| X |  |  | IO |  |  | E1201013 | E1300793 | see individual lists | G. Mueller |  | 2013-08-31 | 2013-11-30 | TBD | M. Heintze | E. Gustafson | B. Bland | G. Billingsley | B. O'Reilly | Jeff Kissel | Kate Gushwa | D. Nolting | M. Levine
| U |  |  | ISC | Custom Optics | L1, H1, I1 | E1300854 |  |  |  |  | 2013-11-04 | 2014-01-15 | TBD
| U |  |  | ISC | RF Sources & Distribution | L1, H1, I1 | E1400081 |  |  |  |  | 2013-12-16 | 2014-01-15 | TBD
| U |  |  | ISC | Demodulators & PFDs | L1, H1, I1 | E1300827 |  |  |  |  | 2013-11-11 | 2014-01-15 | TBD
| C |  |  | ISC | Signal Conditioning Electronics | L1, H1, I1 | E1300973 |  |  |  |  | 2013-11-18 | 2014-01-15 | TBD
| P |  |  | ISC | Common Mode Servos & SM Summing | L1, H1, I1 | [5 empty] | 2013-12-02 | 2014-01-15 | TBD
| P |  |  | ISC | Tip-Tilt Mounts | L1, H1, I1 | [5 empty] | 2013-11-25 | 2014-01-15 | TBD
| C |  |  | ISC | Beam Diverters | L1, H1, I1 | E1400011 |  |  |  |  | 2013-12-02 | 2014-01-15 | TBD
| U |  |  | ISC | Custom Photodetectors | L1, H1, I1 | E1400145 |  |  |  |  | 2013-12-09 | 2014-01-15 | TBD
| P |  |  | ISC | Fast Shutters | L1, H1, I1 | [5 empty] | 2014-01-13 | 2014-03-01 | TBD
| P |  |  | ISC | End Station | L1, H1, I1 | [5 empty] | 2014-02-10 | 2014-03-01 | TBD
| P |  |  | ISC | Vertex Input Section | L1, H1, I1 | [5 empty] | 2014-02-03 | 2014-03-01 | TBD
| P |  |  | ISC | Vertex Output Section | L1, H1, I1 | [5 empty] | 2013-12-16 | 2014-01-15 | TBD
| P |  |  | ISC | Arm Length Stabilization Sys | L1, H1, I1 | [5 empty] | 2014-01-06 | 2014-03-01 | TBD
| P |  |  | ISC | LSC Real-Time Model | L1, H1, I1 | [5 empty] | 2014-01-20 | 2014-03-01 | TBD
| P |  |  | ISC | ASC Real-Time Model | L1, H1, I1 | [5 empty] | 2014-02-10 | 2014-03-01 | TBD
| P |  |  | ISC | Slow Controls | L1, H1, I1 | [5 empty] | 2013-12-16 | 2014-01-15 | TBD
| X |  |  | ISC |  |  | E1300833 | see individual reports | E1400172 | P. Fritschel | Document schedule is per P. Fritschel; Review schedule is proposed to S. Whitcomb (TBC) | 2014-02-10 | 2014-03-01 | TBD | S. Whitcomb | M. Landry | S. Aston | M. Zucker | B. Abbott |  |  | D. Nolting | M. Levine
| C | A |  | PSL | NA | L1 | E1200039 | Notes&Changes E1200039 | section 5 of E1100716 | B. Willke | punch list has been addressed; responses under review | done | done | done? | V. Frolov | P. Fritschel | D. Coyne | M. Landry | B. Lantz
| U |  |  | PSL | NA | H1 | E1300129 | TBW | TBD | B. Willke | docs prepared, review underway | done | 2014-02-15 | TBD | R. Savage | V. Frolov | P. Fritschel | D. Coyne | M. Landry | B. Lantz
| U |  |  |  |  | I1 | E1200385
| X |  |  | PSL |  |  | E1200038 |  |  |  |  | 2013-08-31 | 2013-10-31 | TBD | [7 empty] | D. Nolting | M. Levine
| P |  |  | SEI | HEPI | L1 HAM1 | [5 empty] | 2013-12-31 | 2014-02-01 | TBD
| P |  |  | SEI | HEPI | L1 HAM2 | [5 empty] | 2013-12-31 | 2014-02-01 | TBD
| P |  |  | SEI | HEPI | L1 HAM3 | [5 empty] | 2013-12-31 | 2014-02-01 | TBD
| P |  |  | SEI | HEPI | L1 HAM4 | [5 empty] | 2013-12-31 | 2014-02-01 | TBD
| P |  |  | SEI | HEPI | L1 HAM5 | [5 empty] | 2013-12-31 | 2014-02-01 | TBD
| P |  |  | SEI | HEPI | L1 HAM6 | [5 empty] | 2013-12-31 | 2014-02-01 | TBD
| P |  |  | SEI | HEPI | L1 BSC1 | [5 empty] | 2013-12-31 | 2014-02-01 | TBD
| P |  |  | SEI | HEPI | L1 BSC2 | [5 empty] | 2013-12-31 | 2014-02-01 | TBD
| P |  |  | SEI | HEPI | L1 BSC3 | [5 empty] | 2013-12-31 | 2014-02-01 | TBD
| P |  |  | SEI | HEPI | L1 BSC4 | [5 empty] | 2013-12-31 | 2014-02-01 | TBD
| P |  |  | SEI | HEPI | L1 BSC5 | [5 empty] | 2013-12-31 | 2014-02-01 | TBD
| P |  |  | SEI | HEPI | L1 Corner Pump Station | [5 empty] | 2013-12-31 | 2014-02-01 | TBD
| P |  |  | SEI | HEPI | L1 Xend Pump Station | [5 empty] | 2013-12-31 | 2014-02-01 | TBD
| P |  |  | SEI | HEPI | L1 Yend Pump Station | [5 empty] | 2013-12-31 | 2014-02-01 | TBD
| P |  |  | SEI | HEPI | H1 HAM1 | [5 empty] | 2013-12-31 | 2014-03-15 | TBD
| P |  |  | SEI | HEPI | H1 HAM2 | [5 empty] | 2013-12-31 | 2014-03-15 | TBD
| P |  |  | SEI | HEPI | H1 HAM3 | [5 empty] | 2013-12-31 | 2014-03-15 | TBD
| P |  |  | SEI | HEPI | H1 HAM4 | [5 empty] | 2013-12-31 | 2014-03-15 | TBD
| P |  |  | SEI | HEPI | H1 HAM5 | [5 empty] | 2013-12-31 | 2014-03-15 | TBD
| P |  |  | SEI | HEPI | H1 HAM6 | [5 empty] | 2013-12-31 | 2014-03-15 | TBD
| P |  |  | SEI | HEPI | H1 BSC1 | [5 empty] | 2013-12-31 | 2014-03-15 | TBD
| P |  |  | SEI | HEPI | H1 BSC2 | [5 empty] | 2013-12-31 | 2014-03-15 | TBD
| P |  |  | SEI | HEPI | H1 BSC3 | [5 empty] | 2013-12-31 | 2014-03-15 | TBD
| P |  |  | SEI | HEPI | H1 BSC9 | [5 empty] | 2013-12-31 | 2014-03-15 | TBD
| P |  |  | SEI | HEPI | H1 BSC10 | [5 empty] | 2013-12-31 | 2014-03-15 | TBD
| P |  |  | SEI | HEPI | H1 Corner Pump Station | [5 empty] | 2013-12-31 | 2014-03-15 | TBD
| P |  |  | SEI | HEPI | H1 Xend Pump Station | [5 empty] | 2013-12-31 | 2014-03-15 | TBD
| P |  |  | SEI | HEPI | H1 Yend Pump Station | [5 empty] | 2013-12-31 | 2014-03-15 | TBD
| P |  |  | SEI | HEPI | I1 HAM Pier Units | [5 empty] | 2013-12-31 | 2014-04-26 | TBD
| P |  |  | SEI | HEPI | I1 BSC Pier Units | [5 empty] | 2013-12-31 | 2014-04-26 | TBD
| P |  |  | SEI | HEPI | I1 Pump Stations | [5 empty] | 2013-12-31 | 2014-04-26 | TBD
| X |  |  | SEI | HEPI |  | E1200687 |  |  |  | most common documentation done; all component tests done | 2013-12-31 | 2014-04-26 | TBD
| P |  |  | SEI | HAM ISI | L1 HAM2 | [5 empty] | done | 2013-12-01 | TBD
| P |  |  | SEI | HAM ISI | L1 HAM3 | [5 empty] | done | 2013-12-01 | TBD
| P |  |  | SEI | HAM ISI | L1 HAM4 | [5 empty] | done | 2013-12-01 | TBD
| P |  |  | SEI | HAM ISI | L1 HAM5 | [5 empty] | done | 2013-12-01 | TBD
| P |  |  | SEI | HAM ISI | L1 HAM6 | [5 empty] | done | 2013-12-01 | TBD
| P |  |  | SEI | HAM ISI | H1 HAM2 | [5 empty] | done | 2014-02-16 | TBD
| P |  |  | SEI | HAM ISI | H1 HAM3 | [5 empty] | done | 2014-02-16 | TBD
| P |  |  | SEI | HAM ISI | H1 HAM4 | [5 empty] | done | 2014-02-16 | TBD
| P |  |  | SEI | HAM ISI | H1 HAM5 | [5 empty] | done | 2014-02-16 | TBD
| P |  |  | SEI | HAM ISI | H1 HAM6 | [5 empty] | done | 2014-02-16 | TBD
| P |  |  | SEI | HAM ISI | I1 HAM2 | [5 empty] | 2013-12-31 | 2014-03-30 | TBD
| P |  |  | SEI | HAM ISI | I1 HAM3 | [5 empty] | 2013-12-31 | 2014-03-30 | TBD
| P |  |  | SEI | HAM ISI | I1 HAM4 | [5 empty] | 2013-12-31 | 2014-03-30 | TBD
| P |  |  | SEI | HAM ISI | I1 HAM5 | [5 empty] | 2013-12-31 | 2014-03-30 | TBD
| P |  |  | SEI | HAM ISI | I1 HAM6 | [5 empty] | 2013-12-31 | 2014-03-30 | TBD
| X |  |  | SEI | HAM ISI |  | E1200686 |  |  |  | All common documentation done; all H1 & L1 test docs done; I1 test docs to be done by end of Dec-2013 | 2013-12-31 | 2014-03-30 | TBD
| U |  |  | SEI | BSC ISI | L1 BSC1 | [5 empty] | 2013-12-01 | 2014-01-15 | TBD
| U |  |  | SEI | BSC ISI | L1 BSC2 | [5 empty] | 2013-12-01 | 2014-01-15 | TBD
| U |  |  | SEI | BSC ISI | L1 BSC3 | [5 empty] | 2013-12-01 | 2014-01-15 | TBD
| U |  |  | SEI | BSC ISI | L1 BSC4 | [5 empty] | 2013-12-01 | 2014-01-15 | TBD
| U |  |  | SEI | BSC ISI | L1 BSC5 | [5 empty] | 2013-12-01 | 2014-01-15 | TBD
| U |  |  | SEI | BSC ISI | H1 BSC1 | [5 empty] | 2013-12-01 | 2014-02-26 | TBD
| U |  |  | SEI | BSC ISI | H1 BSC2 | [5 empty] | 2013-12-01 | 2014-02-26 | TBD
| U |  |  | SEI | BSC ISI | H1 BSC3 | [5 empty] | 2013-12-01 | 2014-02-26 | TBD
| U |  |  | SEI | BSC ISI | H1 BSC9 | [5 empty] | 2013-12-01 | 2014-02-26 | TBD
| U |  |  | SEI | BSC ISI | H1 BSC10 | [5 empty] | 2013-12-01 | 2014-02-26 | TBD
| U |  |  | SEI | BSC ISI | I1 BSC1 | [5 empty] | 2014-04-01 | 2014-04-15 | TBD
| U |  |  | SEI | BSC ISI | I1 BSC2 | [5 empty] | 2014-04-01 | 2014-04-15 | TBD
| U |  |  | SEI | BSC ISI | I1 BSC3 | [5 empty] | 2014-04-01 | 2014-04-15 | TBD
| U |  |  | SEI | BSC ISI | I1 BSC4 | [5 empty] | 2014-04-01 | 2014-04-15 | TBD
| U |  |  | SEI | BSC ISI | I1 BSC5 | [5 empty] | 2014-04-01 | 2014-04-15 | TBD
| X |  |  | SEI | BSC ISI |  | E1200685 |  |  |  | most documentation done; all H1 & L1 test docs done | 2014-04-01 | 2014-04-15 | TBD
| X |  |  | SEI |  |  | E1200684 | see individual reports | see individual lists | K. Mason |  | 2014-04-01 | 2014-04-26 | TBD | D. Coyne | B. O'Reilly | C. Guido | C. Osthelder |  |  |  | D. Nolting | M. Levine
| C |  |  | SUS | OMC | L1 OMC | E1400034
| C |  |  | SUS | OMC | H1 OMC | E1400055
| C |  |  | SUS | OMC | I1 OMC | E1400158
| C |  |  | SUS | OMC |  | E1201043 | see individual reports | see individual lists |  | ~90% of common docs done - to be completed 1/15/2014; testing done (phase3b L1, phase 1b H1 & I1); testing docs to be completed 1/15/2014 review of all 3 units to be completed 2/15/2014 | 2014-01-15 | 2/15/2014 - 3 units | TBD
| C |  |  | SUS | HSTS | L1 MC1 | E1400109
| C |  |  | SUS | HSTS | L1 MC2 | E1201042 | Notes&Changes E1201042 | Notes&Changes E1201042?
| C |  |  | SUS | HSTS | L1 MC3 | E1400113
| C |  |  | SUS | HSTS | L1 PRM | E1400114
| C |  |  | SUS | HSTS | L1 PR2 | E1300513 | Notes&Changes E1300513 | Notes&Changes E1300513?
| C |  |  | SUS | HSTS | L1 SR2 | E1400117
| C |  |  | SUS | HSTS | L1 SRM | E1400116
| C |  |  | SUS | HSTS | H1 MC1 | E1400118
| C |  |  | SUS | HSTS | H1 MC2 | E1400119
| C |  |  | SUS | HSTS | H1 MC3 | E1400120
| C |  |  | SUS | HSTS | H1 PRM | E1400121
| C |  |  | SUS | HSTS | H1 PR2 | E1400122
| C |  |  | SUS | HSTS | H1 SR2 | E1400124
| C |  |  | SUS | HSTS | H1 SRM | E1400123
| C |  |  | SUS | HSTS | I1 MC1 | E1300514 | In process - Notes&Changes E1300514
| C |  |  | SUS | HSTS | I1 MC2 | E1400125
| C |  |  | SUS | HSTS | I1 MC3 | E1400126
| C |  |  | SUS | HSTS | I1 PRM | E1300497 | In process - Notes&Changes E1300497
| C |  |  | SUS | HSTS | I1 PR2 | E1400127
| C |  |  | SUS | HSTS | I1 SR2 | E1400129
| C |  |  | SUS | HSTS | I1 SRM | E1400128
| C |  |  | SUS | HSTS |  | E1201040 | Notes&Changes E1201047 | see individual lists |  | 2 of 21 units done; balance to be reviewed 2/15 - 4/15/2014 | done for common & 2 examples | done - 2 units 4/15/2014 - 19 units | TBD
| C |  |  | SUS | HLTS | L1 PR3 | E1300836
| C |  |  | SUS | HLTS | L1 SR3 | E1400115
| C |  |  | SUS | HLTS | H1 PR3 | E1300844
| C |  |  | SUS | HLTS | H1 SR3 | E1400161
| C |  |  | SUS | HLTS | I1 PR3 | E1400159
| C |  |  | SUS | HLTS | I1 SR3 | E1400160
| C |  |  | SUS | HLTS |  | E1201041 |  | see individual lists |  | common docs done; testing docs ready for 2 units; complete review of 1st 2 units nov-2013 Then review balance of 4 2/15-4/15/2014 | 2013-11-01 | 12/1/2013 - 2units 4/15/2014 - 4 units | TBD
| C |  |  | SUS | BS | L1 BS | E1300699 | in process - Notes&Changes E1300699
| C |  |  | SUS | BS | H1 BS | E1300712 | in process - Notes&Changes E1300712
| C |  |  | SUS | BS | I1 BS | E1400157
| C |  |  | SUS | BS |  | E1201039 | Notes&Changes E1201039 | see individual lists |  | 2 units reviewed; balance of 1 unit to be reviewed 2/15-4/15/2014 | done for common & 2 examples | done - 2 units 4/15/2014 - 1 unit | TBD
| C |  |  | SUS | Quad | L1 ITMX | E1300916
| C |  |  | SUS | Quad | L1 ITMY | E1300917
| C |  |  | SUS | Quad | L1 ETMX | E1400080
| C |  |  | SUS | Quad | L1 ETMY | E1400131
| U |  |  | SUS | Quad | H1 ITMX | E1400146
| U |  |  | SUS | Quad | H1 ITMY | E1400147
| C |  |  | SUS | Quad | H1 ETMX | E1300908
| C |  |  | SUS | Quad | H1 ETMY | E1300866
| U |  |  | SUS | Quad | I1 #1 | E1400148
| U |  |  | SUS | Quad | I1 #2 | E1400149
| U |  |  | SUS | Quad | I1 #3 | E1400150
| U |  |  | SUS | Quad | I1 #4 | E1400151
| C |  |  | SUS | Quad |  | E1201038 |  |  |  | common docs and 2 testing docs to be completed 12/1/2013; review of common docs and 2 units by 1/15/2014 Then review balance of 9 units 2/15-4/15/2014 | 2013-12-01 | 1/15/2014 - 2 units 4/15/2014 - 10 units | TBD
| X |  |  | SUS |  |  | E1200482 | see individual reports | see individual lists | N. Robertson |  | 2014-01-15 | 2014-04-15 | TBD | C. Torrie | F. Matichard | C. Ramet | A. Heptonstall | J. Lewis | R. Abbott |  | D. Nolting | M. Levine
| 173 | # entries
| 0 | # blank entries
| 11 | # Not Applicable (X)
| 162 | # reviews
| 64 | # Pending
| 40 | # Underway
| 58 | # Completed
162
Formulas:
Schedule = [Accepted/ Punch List Created]-4*7
Schedule = MAX(P12:[Schedule, row above])
Accepted/ Punch List Created = MAX(Q4:[Accepted/ Punch List Created, row above])
Accepted/ Punch List Created = [Accepted/ Punch List Created, row above]
Punch list completed = MAX(R26:[Punch list completed, row above])