## Sheet1
SLC ACCEPTANCE DOCUMENTATION REVIEW
per M1100282
[8 empty] | requirements and design documentation, materials and fabrication |  | parts inventoried, travelers |  | assembly and installation procedures |  | acceptance test documentation and results |  | Manuals--safety
| acceptance document | document link/reference | status/comments | Responsible | ETC hours | actual other hours | actual Smith hrs | item | % com | item | % com | item | % com | item | % com | item | % com
| Documentation Tree Root DCC entry | E1300270 aLIGO AOS SLC/VP Acceptance Directory | complete
Common Documents
| Scattered Light Calculations | MatLab files | update TBD | Virginio | 80 | 80
T1300818-v1_Riley-Smith BRDF measurement - final1_mrs
T1300819-v1_Dan Riley BRDF measurement - final1
| DRD | T070061 Stray Light Control (SLC) Design Requirements | done |  |  |  |  | 1 | 100%
| Specifications | E0900023 Process for Manufacturing Cantilever Spring Blades for AdvLIGO
Q1100003 Acceptable Quality Level (AQL) for Inspection of LIGO Components
E1100842-v7 MIRROR FINISH SS SPEC
E0900364 Metal Components for use in the Advanced LIGO Vacuum System
Arm Cavity Baffle (ACB)
| Final Design Document (FDD) | T1000747 SLC Arm Cavity Baffle FDR | done |  |  |  |  | 1 | 100%
| final design report | E1100050 Responses to AOS SLC ACB FDR Questions
| supporting analyses/models | E1300345 Repository for ACB Baffle Supporting Analyses/models | done |  |  |  |  | 1 | 100%
T070089-v1_Wide-angle scatter from LIGO arm cavities
T1100056 Arm Cavity Baffle Edge Scatter
T1100113 Wide Angle Scatter From Hr Surface Of Test Mass
T1300043 Arm Cavity Baffle Shift with Alignment Target
E1300070 ACB Balance Weights
T1300400 arm-cavity-bafffle_blade_D1002608-V4
T1300828-v1_ALS-photodetector on ACB
T1300403 ETM_wide-angle_scatter_AC_ZEMAX
T1300404 ACB scatter
T1300405 ACB edge scatter, porcelain vs oxidized SS
T1300823-v1_wide angle scatter_ITMX_H1_power
T1300824-v1_wide angle scatter_ETMX_H1_power
T1300829-v1_ACB ETM wide angle scatter power summary
T1300406 Wide Angle Scatter from ITM
T1200425 Wide Angle Scatter from ETM HR
T1300699_ACB scatter various materials
T1300691-v1_ACB upgrade SS with black glass
D1300588 ACB 1 hole skin with black glass
T1300589-v1 ACB Black Glass Hybrid Baffle
L1100202-v2 hybrid black glass polished ss ACB
|  | ACB Vibration Test Report | report TBD | Virginio | 24 | 24 | [7 empty] | 1 | 0%
T1300700-v1_ ACB DLC coating on SS
T1300716-v1_ACB Multi-AR coating on SS
T1300731-v1 comparison of DLC and mAR coating on ACB
T1300827-v1_ACB shift with target
| drawing/document tree/list |  | TBD | lisa/Nichole | 8 | 8 |  | 1 | 75%
| parts list (BOM) | C1101402 Arm Cavity Baffle Statement of Work (Machined Parts) | [7 empty] | 1 | 100%
| spares list |  | TBD | lisa/Nichole | 8 | 8 |  |  |  | 1 | 50%
| design drawings, schematics, interfaces, etc. | E1300348 Repository for ACB Design Drawings, Interfaces, etc. | update TBD | Lisa/Eddie | 24 | 24
D1001011: SLC ARM CAVITY BAFFLE SUSPENSION ASSY
D1200275: AdLIGO_AOS_ACB-SUSPENSION ASSY, BSC1-BSC3_H1 L1
|  | SLC 1 HOLE RIGHT ARM CAVITY BAFFLE ASSY at BSC5 and BSC10 | TBD | Eddie | 40 | 40
| SW Vault files | D1001011: SLC ARM CAVITY BAFFLE SUSPENSION ASSY | update TBD | Lisa/Eddie | 16 | 16
| Specifications | See Common Documents
T1300826-v1_Work Sheet_ thin PD wall
|  | E1100867 Advanced LIGO AOS Arm Cavity Baffle Assembly Procedure | update TBD | Lisa/Scott | 8 | 8 | [5 empty] | 1 | 80%
|  | E1101220 ACB Cabling Connections | [9 empty] | 1 | 100%
| Installation plan/procedure(s) | E1100810 Arm Cavity Baffle Installation/De-installation Procedure | update TBD |  | 8 | 8 | [5 empty] | 1 | 80%
| Test & Commissioning Doc Tree |  | TBD | Jeff Lewis | 8 | 8
| Test plan/procedure(s) | E1000892 Arm Cavity Baffle Fabrication, Installation, and Test Plan | update TBD | Lisa | 4 | 4
| User Interface Software SVN | NA
| User's Manual(s) | NA
| Troubleshooting Guide | NA
| Safety Docs | E1000890 SLC Arm Cavity Baffle Install Hazard Analysis | complete | [12 empty] | 1 | 100%
ACB Documents:
| acceptance document | E1300212 SLC Acceptance Documentation | update TBD | Lisa | 16 | 16 | [7 empty] | 1 | 75%
| ICS inventory |  | TBD | Nichole | 8 | 8 |  |  |  | 1 | 50%
| S-numbers |  | TBD | Nichole | 8 | 8
| Test results | E1300346 Repository for ACB Baffle Test Results
E1000648-v1_AC Baffle_SEI_Couplings_LASTI
C1301585 ELECTROLESS NICKEL PLATE_D1001006 ACB BLADE
E1100583 SEM Examination of Spotted and Rusted Cantilever Blades
E1300070 ACB Blade Balance Weight
https://alog.ligo-wa.caltech.edu/aLOG/index.php?callRep=4106
https://alog.ligo-wa.caltech.edu/aLOG/index.php?callRep=3244
https://alog.ligo-wa.caltech.edu/aLOG/index.php?callRep=2071
https://alog.ligo-wa.caltech.edu/aLOG/index.php?callRep=3170
https://alog.ligo-wa.caltech.edu/aLOG/index.php?callRep=2607
|  | E1300373 Install ACB LLO BSC1 Test | TBD | Vargas/Hanson | 4 | 4 | [7 empty] | 1 | 50%
|  | E1300374 Install ACB LLO BSC3 Test | TBD | Vargas/Hanson | 4 | 4 | [7 empty] | 1 | 50%
|  | E1300375 Install ACB LLO BSC4 Test | TBD | Vargas/Hanson | 4 | 4 | [7 empty] | 1 | 0%
|  | E1300376 Install ACB LLO BSC5 Test | TBD | Vargas/Hanson | 4 | 4 | [7 empty] | 1 | 0%
|  | E1300377 Install ACB LHO BSC1 Test | TBD | Vo/Doug | 4 | 4 | [7 empty] | 1 | 0%
|  | E1300378 Install ACB LHO BSC3 Test | TBD | Vo/Doug | 4 | 4 | [7 empty] | 1 | 0%
|  | E1300379 Install ACB LHO BSC9 Test | TBD | Vo/Doug | 4 | 4 | [7 empty] | 1 | 0%
|  | E1300380 Install ACB LHO BSC510 Test | TBD | Vo/Doug | 4 | 4 | [7 empty] | 1 | 0%
|  | T1100637 ACB Cabling Test Procedure | update TBD | Mohanna |  |  |  | 1 | 100%
|  | Fritschel--ISC- one-arm test PD results | Report TBD | Vo/Fritschel
Channel/Signal List and Calibrations
| Beam Splitter Elliptical Baffle |  | complete |  |  |  |  | 1 | 100%
| Final Design Document (FDD) | T1200313 BS Elliptical Baffle FD | done
| final design report | M1200268 RODA for inclusion of Elliptical baffle on BS suspension structure | done
| supporting analyses/models | E1300344 Repository for BS Elliptical Baffle Supporting Analyses/models
T1300538 BS_wide-angle_scatter_ZEMAX
T1300539 BS wide-angle Scatter Displacement Noise Summary
T1000090 advanced LIGO baffle design using SIS
T1300401 wide angle scatter_BS_L1_power
T1300407 BS Elliptical baffle scatter
T1300408 BS Elliptical Baffle Design
T1300692-v1_ BS Elliptical baffle scatter_black glass hybrid
T1300695-v1_BS Elliptical Baffle--Black Glass Design Scattering Analysis
T1300816-v1_BS Elllip Baf scatter overlap integral
T1300821-v1_BS elliptical baffle-3 Model
| prototype tests | Calum | report TBD | Calum | 8 | 8
T1300822-v1_ACB Suspension Prototype SLCS.InternalModes.1.1-1
| drawing/document tree/list |  | TBD | lisa/Nichole | 8 | 8 |  | 1 | 75%
| parts list (BOM) | E1200520 BOM for BS ELLIPTICAL BAFFLE ASSY | complete | [6 empty] | 1 | 100%
| spares list |  | TBD | Nichole | 8 | 8 |  |  |  | 1 | 90%
| design drawings, schematics, interfaces, etc. | E1300355 Repository for BS Elliptical Baffle Design Drawings, Interfaces, etc. | update TBD | Kurt | 8 | 8
D1200750: aLIGO, AOS, BS ELLIPTICAL BAFFLE ASSY
| SW Vault files | D1200750: aLIGO, AOS, BS ELLIPTICAL BAFFLE ASSY | update TBD | Kurt | 8 | 8
| Specifications | See Common Documents
| Assembly procedure(s) | E1200660 AOS SLC BS Elliptical Baffle Installation Procedure | update TBD | Kurt/Lisa | 8 | 8 | [5 empty] | 1 | 80%
| Installation plan/procedure(s) | E1200660 AOS SLC BS Elliptical Baffle Installation Procedure | update TBD | [8 empty] | 1 | 80%
| Test & Commissioning Doc Tree |  | TBD | Jeff Lewis | 8 | 8
| Test plan/procedure(s) | E1200661 SLC BS Elliptical Baffle Fabrication, Installation, and Test Plan | update TBD | Lisa | 4
| User Interface Software SVN | NA
| User's Manual(s) | NA
| Troubleshooting Guide | NA
| Safety Docs | E1200659 SLC BS Elliptical Baffle Install Hazard Analysis | update TBD | Lisa | 8 | 8 | [9 empty] | 1 | 75%
Beam Splitter Elliptical Baffle Documents:
| acceptance document | E1300212 SLC Acceptance Documentation | update TBD | Lisa | 8 | 8 | [7 empty] | 1 | 75%
| ICS inventory |  | TBD | Nichole | 8 | 8 |  |  |  | 1 | 90%
| S-numbers |  | TBD | Nichole | 8 | 8
| Test results | E1300426 Repository for BS Elliptical Baffle Test Results
|  | E1300368 Install BS Elliptical Baffle LLO BSC2 X&Y Test | TBD | Vargas/Hanson | 4 | 4 | [7 empty] | 1 | 90%
|  | E1300371 Install BS Elliptical Baffle LHO BSC2 X&Y Test | TBD | Vo/Doug | 4 | 4 | [7 empty] | 1 | 90%
| Channel/Signal List and Calibrations | NA
ITM Elliptical Baffle
| Final Design Document (FDD) | T1100446 ITM Elliptical Baffle FD | update ongoing | Lisa | 24 | 24 |  | 1 | 75%
| final design report | E1300303 ITM Ellip Baf Responses to committee
| supporting analyses/models | E1300343 Repository for ITM Elliptical Baffle Supporting Analyses/models | complete
E1300071 ITM Ellip Baf Blade Balance Weight
T1300402 ITM Ellip Baf_blade_D1002753-v5
T1000090 advanced LIGO baffle design using SIS
T1300324 ITM Elliptical Baffle Scatter
T1300402_ITM Ellip Baf_blade_D1002753-v5
T1300591-v1 ITM Elliptical Baffle Black Glass Hybrid
T1300685-v1 ITM Elliptical Baffle Scatter Interference Effects
T1300689-v1 ITM Elliptical baffle scatter_black glass hybrid
| prototype tests | T1200419 ITM Ellipical Baffle (ITM_EB) First Article Longitudinal Transmissibility with Damper | done | [10 empty] | 1 | 100%
|  | T1300325 Stray Light Control Noise Estimation, ITM Elliptical Baffle | done | [10 empty] | 1 | 100%
| drawing/document tree/list |  | TBD | lisa/Nichole | 8 | 8 |  | 1 | 75%
| parts list (BOM) | E1101039 BOM_aLIGO AOS ITM ELLIPTICAL BAFFLE FINAL ASSY | [7 empty] | 1 | 100%
| spares list |  |  | lisa/Nichole | [5 empty] | 1 | 90%
| design drawings, schematics, interfaces, etc. | E1300354 Repository for ITM Elliptical Baffle Design Drawings, Interfaces, etc. | TBD | Lisa/Eddie | 16 | 16
D0900428 aLIGO Systems, LBSC2-L1 Top Level Chamber Assembly
D1003238-v5: aLIGO AOS ITM ELLIPTICAL BAFFLE FINAL ASSY H1/L1
D1101806: aLIGO ITM ELLIPTICAL BAFFLE ASSEMBLY
E1101220-v1_ACB Cabling Connections
D1101885: aLIGO AOS ITM ELLIPTICAL BAFFLE SUSPENSION ASSY
| SW Vault files | D0900428 aLIGO Systems, LBSC2-L1 Top Level Chamber Assembly
|  | D1003238-v5: aLIGO AOS ITM ELLIPTICAL BAFFLE FINAL ASSY H1/L1 | update TBD | Lisa/Eddie | 16 | 16
| Specifications | See Common Documents
| Assembly procedure(s) | E1200677 ITM Elliptical Baffle Assembly Procedure | update TBD | Scott | 16 | 16 | [5 empty] | 1 | 80%
| Installation plan/procedure(s) | E1101021 ITM Elliptical Baffle Installation Procedure | update TBD | Scott | 16 | 16 | [5 empty] | 1 | 80%
| Test & Commissioning Doc Tree |  | TBD | Jeff Lewis | 8 | 8 | [7 empty] | 1 | 0%
| Test plan/procedure(s) | E1101022 ITM Elliptical Baffle Test Plan | update TBD | Lisa | 4 | 4
| User Interface Software SVN | NA
| User's Manual(s) | NA
| Troubleshooting Guide | NA
| Safety Docs | E1101018 ITM Elliptical Baffle Assembly & Install Hazard Analysis | done | [12 empty] | 1 | 100%
ITM Elliptical Baffle Documents:
| acceptance document | E1300212 SLC Acceptance Documentation | update TBD | Lisa | 16 | [8 empty] | 1 | 75%
| ICS inventory |  | TBD | Nichole | [5 empty] | 1 | 100%
| S-numbers |  | TBD | Nichole | 8 | 8
| Test results | E1300427 Repository for ITM Elliptical Baffle Test Results
|  | E1300381 Install ITM Elliptical Baffle LLO BSC2 X&Y Test | TBD | Vargas/Hanson | 4 | 4 | [7 empty] | 1 | 75%
|  | E1300405 Install ITM Elliptical Baffle LHO BSC2 X&Y Test | TBD | Vargas/Hanson | 4 | 4 | [7 empty] | 1 | 0%
| Channel/Signal List and Calibrations | NA
Manifold/Cryopump and Mode Cleaner Tube Baffles
| Final Design Document (FDD) | T1100165 Manifold/Cryopump and Mode Cleaner Tube Baffles FDR | update TBD | Lisa | 40 | 40 |  | 1 | 75%
| final design report | M1200018 RODA Photon Calibrator and Stray Light Control Optical and Mechanical Interfaces
M1200070 Advanced LIGO Committee Report for the AOS SLC Manifold/Cryopump and Mode Cleaner Tube Baffles FDR
| supporting analyses/models | E1300342 Repository for Manifold/Cryopump & Mode Cleaner Baffles Supporting Analyses/models | complete
T1300411 Manifold/Cryopump Baffle blade spring D902817-v4
T1300412 Manifold-Cryopump Baffle Scatter
T1300413 ETM Manifold/cryopump Baffle Mis-alignment IFO Beam Power Loss
T1300811-v1_Manifold-Cryo_baffle scatter ETM-annulus
T1300810-v1_MC Tube Baffle Scatter
T1300830-v1_MC tube baffle beam clearance
E1300420-v1 Manifold-cryo baf Blade Balance Weight
| prototype tests | T1300530 aLIGO CryoPump Baffle Suspension, Ring-down Measurements | done | [10 empty] | 1 | 100%
|  | T1300529 CryoPump Baffle (CPB) Suspension Vertical Transmissibility, eLog Extract | done | [10 empty] | 1 | 100%
T1300813-v1_CPBS.Proto.Transmissibility.Total.Y.01-02
T1300814-v1_CPBS.Proto.Transmissibility.Total.Z.01
|  | T1300528 CryoPump Baffle (CPB) Suspension Transmissibility Along Beam Direction, eLog Extract | done | [10 empty] | 1 | 100%
| drawing/document tree/list |  | TBD | lisa/Nichole | 8 | 8 |  | 1 | 75%
| parts list (BOM) | D1003181 aLIGO_Manifold Cryo Baffle_Assembly, ETMX H1 | TBD | lisa/Nichole | [5 empty] | 1 | 100%
|  | D1003228 aLIGO_Manifold Cryo Baffle_Assembly, ETMY H1 | TBD | lisa/Nichole | [5 empty] | 1 | 100%
T1300815-v1_Fastener list Manifold-cryo baf
E1100422 BOM - aLIGO Manifold Cryopump Tube Baffle Assembly
E1000831 BOM - aLIGO Mode Cleaner Tube Baffle Top Assembly
| spares list |  | TBD | lisa/Nichole | [5 empty] | 1 | 100%
| design drawings, schematics, interfaces, etc. | E1300352 Repository for Manifold/Cryopump & Mode Cleaner Tube Baffle Design Drawings, Interfaces, etc. | TBD | Lisa/Eddie | 16 | 16
D0902617-v2: aLIGO_Manifold_Cryo_Baffle_Assembly
D1002061-v2: aLIGO_AOS_Manifold Cryo Baffle_Weldment Assembly
D1002084-v2: aLIGO_AOS_Manifold Cryo Baffle_Outer Ring Assy
D1002402-v2: aLIGO_Manifold Cryo Baffle_Balance Weight Assy
| SW Vault files | D1003228 aLIGO_Manifold Cryo Baffle_Assembly, ETMY H1 | update TBD | Lisa/Eddie | 8 | 8
|  | D1003181 aLIGO_Manifold Cryo Baffle_Assembly, ETMX H1 | update TBD | Lisa/Eddie | 8 | 8
|  | D0902617-v2: aLIGO_Manifold_Cryo_Baffle_Assembly | update TBD | Lisa/Eddie | 16 | 16
| Specifications | See Common Documents
E0900048 Welding Specification for Weldments used within the Advanced LIGO Vacuum System
| Assembly procedure(s) | E1100607 SLC Manifold Cryopump Baffle Assembly and Installation Document | done | [8 empty] | 1 | 100%
E1100718 Mode Cleaner Tube Baffle Assembly and Installation Procedure
| Installation plan/procedure(s) | E1100481 Mode Cleaner Tube Baffle & Manifold/Cryopump Baffle Fabrication, Installation, and Test Plan
|  | E1100607 SLC Manifold Cryopump Baffle Assembly and Installation Document | done | [8 empty] | 1 | 100%
|  | E1100718 Mode Cleaner Tube Baffle Assembly and Installation Procedure | update TBD | lisa/Nichole | 16 | 16 | [5 empty] | 1 | 100%
| Test & Commissioning Doc Tree |  | TBD | Jeff Lewis | 8 | 8 |  | 1 | 75% |  |  |  |  | 1 | 0%
| Test plan/procedure(s) | E1100481 Mode Cleaner Tube Baffle & Manifold/Cryopump Baffle Fabrication, Installation, and Test Plan | update TBD | Lisa | 4 | 4
| User Interface Software SVN | NA
| User's Manual(s) | NA
| Troubleshooting Guide | NA
| Safety Docs | E1100491 SLC Mode Cleaner Tube Baffle Install Hazard Analysis | update TBD | lisa/Nichole | 4 | 4 | [9 empty] | 1 | 75%
|  | E1100482 SLC Manifold/Cryopump Baffle Install Hazard Analysis | update TBD | lisa/Nichole | 8 | 8 | [9 empty] | 1 | 75%
Manifold/Cryopump and Mode Cleaner Tube Baffles Documents:
| acceptance document | E1300212 SLC Acceptance Documentation | done | [10 empty] | 1 | 100%
| ICS inventory |  | TBD | Nichole | 8 | 8 |  |  |  | 1 | 80%
| S-numbers |  | TBD | Nichole | 8 | 8
| Test results | E1300423 Repository for Manifold/Cryo Baffle Test Results
|  | E1300424-v1 Thickness Inspection D0902817–v4 Blade Manifold-Cryo Baf | done | [10 empty] | 1 | 100%
T1300812-v1_Manifold-cryo-baf_Blades_Weight_Req
|  | E1300420 Manifold/cryo baffle Blade Balance Weight | done | [10 empty] | 1 | 100%
T1300809-v1-_Circularity Measurements
|  | E1300385 Install Manifold/Cryo Baf LLO ITM X Test | TBD | Vargas | 4 | 4 | [7 empty] | 1 | 0%
|  | E1300386 Install Manifold/Cryo Baf LLO ITM Y Test | TBD | Vargas | 4 | 4 | [7 empty] | 1 | 0%
|  | E1300387 Install Manifold/Cryo Baf LLO ETM X Test | TBD | Vargas | 4 | 4 | [7 empty] | 1 | 0%
|  | E1300388 Install Manifold/Cryo Baf LLO ETM Y Test | TBD | Vargas | [9 empty] | 1 | 0%
|  | E1300407 Install Manifold/Cryo Baf LHO ITM X Test | TBD | Vo | [9 empty] | 1 | 0%
|  | E1300408 Install Manifold/Cryo Baf LHO ITM Y Test | TBD | Vo | [9 empty] | 1 | 0%
|  | E1300409 Install Manifold/Cryo Baf LHO ETM X Test | TBD | Vo | [9 empty] | 1 | 0%
|  | E1300410 Install Manifold/Cryo Baf LHO ETM Y Test | TBD | Vo | 4 | 4 | [7 empty] | 1 | 0%
|  | T1300787-v1_Cryo-baf B-K measurement | done
T1300529-v1_Cryo-pump suspension vertical transmissibility
|  | T1300788-v1_Cryo-Pump Baffle porcelainized steel chipping | done
| Channel/Signal List and Calibrations | NA
Output Faraday Isolator (OFI)
| Final Design Document (FDD) | T1000181 Stray Light Control (SLC)-- Output Faraday Isolator Final Design | update ongoing | Lisa | 24 | 24 |  | 1 | 90%
| final design report | T1000308 Stray Light Control (SLC)-- Output Faraday Isolator FDR Responses
L1000362 Response to the Output Faraday Isolator (OFI) Final Design Review Report
| supporting analyses/models | E1300341 Repository for OFI supporting analyses/models | complete
T1300218 Creep of SLC Maraging Steel Suspension Blades
E1300043 OFI Balance Weights and Locations
T1300414 Output Faraday Isolator Blade Creep
T1300415 Output Faraday Isolator Upper Blade D0900541-v4
T1300794-v1_OFI blade matching light table
T1300416 OFI Beam Height
T1300793-v1_OFI SPACER HEIGHT
T1300795-v1_Squeezer BS deviation angle
T1300796-v1_AR coating_KLC
T1300797-v1_20mm-aper_Brewster-polarizer
D1300784-v1_190-11205-1001 REV 01 aperture dwg
D1300785-v1_190-11205-1001 REV 01_aLIGO-Faraday-rotator
T1300474-v1 H1 SIGNAL RECYCLING CAVITY beam size_3-11-13
T1000558 Output Faraday Isolator (OFI) Table Deflection and Modal Analysis
T1300417 Extinction Ratio of Output Faraday Isolator vs Input Angle
T1300418 TFP Polarizer Wedge Deviation OFI
T1300475-v1 OFI scattering
T1300713-v1_OFI Balance Weights for heavy table D0900015-v5
T1300791-v1_OFI glint
| prototype tests | OFI Vibration Test Report | TBD | Virginio | 24 | 24 | [7 empty] | 1 | 100%
| drawing/document tree/list |  | TBD | lisa/Nichole | 8 | 8 |  | 1 | 75%
| parts list (BOM) | D0900136 Output Faraday Isolator Assy | [7 empty] | 1 | 100%
| spares list |  | TBD | lisa/Nichole | [5 empty] | 1 | 100%
| design drawings, schematics, interfaces, etc. | E1300351 Repository for OFI Design Drawings, Interfaces, etc. | TBD | Lisa/Eddie | 16 | 16
D0900136-v5_AdLIGO_AOS_Faraday Isolator Assembly (HR).PDF
D0900048: Faraday Isolator Damper Holder Assembly
D0900170: Faraday Isolator Earthquake Crossbar Assembly
D0900566: Faraday Isolator Upper Blade Clamp Top
D0900579: Faraday Isolator Blade Guard Assy
D0900586: Faraday Isolator Up Wire Assembly
D0900623: Faraday Isolator Table Assembly
D0900655: Structural Weldment Assembly (OMCS)
D0901514: Faraday Isolator Blade Clamp Platform
D0902845: Faraday Isolator Refl Baffle
D1002256: AdLIGO_AOS_D0900136_Earthquake Crossbar-In Assy
| SW Vault files | D0900136-v5_AdLIGO_AOS_Faraday Isolator Assembly | update TBD | Lisa/Eddie | 16 | 16
| Specifications | See Common Documents
E1300340 Repository for OFI Specification Documents
E1000116 Output Faraday Rotator Component Specification
E1000398 Thin Film Polarizer for Advanced LIGO Output Faraday Isolator
E1200098 1.0 inch OFI Wedge Prism Specification
| Assembly procedure(s) | E1201074 Output Faraday Isolator Assembly and Alignment Procedure | done | [8 empty] | 1 | 100%
| Installation plan/procedure(s) | E1300056 Output Faraday Isolator Installation and Final Alignment Procedure | done | [8 empty] | 1 | 100%
| Test & Commissioning Doc Tree |  | TBD | Jeff Lewis | 8 | 8 | [7 empty] | 1 | 0%
| Test plan/procedure(s) | T1000192 Output Faraday Isolator Test Plan | update TBD | Lisa | 4 | 4
| User Interface Software SVN | NA
| User's Manual(s) | NA
| Troubleshooting Guide | NA
| Safety Docs | E1300283 OFI Assembly & Installation Hazard Analysis | update TBD | Lisa | 8 | 8 | [9 empty] | 1 | 75%
Output Faraday Isolator Documents:
| acceptance document | E1300212 SLC Acceptance Documentation | update TBD | Lisa | 16 | 16 | [7 empty] | 1 | 75%
| ICS inventory |  | TBD | Nichole | [5 empty] | 1 | 100%
| S-numbers |  | TBD | Nichole | 8 | 8
| Test results | E1300428 Repository for Output Faraday Isolator Test Results
|  | New Blade Weight Test & analysis | TBD | Jeff Lewis/Gerardo | 4 | 4 | [7 empty] | 1 | 0%
|  |  | TBD | MR Smith | 8 | 8 | 8 | [6 empty] | 1 | 0%
C1301597 certificate of conform_KLC pol prism
L1000120-v1_Mike Burda_EOT e-mail microroughness of TGG
T1000558-v2 OFI table static and modal-v2
T1300342-v1 OFI Optical test results_LLO
T1300346-v1_OFI Vendor Test Results_Brewster Polarizer
T1300347-v1_OFI Vendor Test Results_Faraday Rotator
T1300789-v1_OFI Wedge Prism Reflectance Data
T1300792-v1_polarizer-wavefront_KLC
T1300419 OFI 1st Article Data_hanford iLog
|  | E1300389 Align/Install Output Faraday Isolator LLO Test | TBD | Guido/Vargas | 4 | 4 | [7 empty] | 1 | 90%
|  | E1300390 Align/Install Output Faraday Isolator LHO Test | TBD | Doug/Vo | 4 | 4 | [7 empty] | 1 | 0%
| Channel/Signal List and Calibrations | NA
Signal Recycling Cavity Baffles
| Final Design Document (FDD) | T1100445 SLC: Signal Recycling Cavity Baffles Final Design | update TBD | Lisa | 40 | 40 |  | 1 | 75%
| final design report | E1300347 Repository for Signal Recycling Cavity Baffle Final Design Report
E1300339 Signal Recycling Cavity Final Design Docs
L1200091 AOS SLC Signal Recycling Cavity Baffles FDR Committee Questions
M1200073 SLC Signal Recycling Cavity Baffles FDR Committee Report
L1200106 Signal Recycling Cavity Baffles Final Design- Responses to Review Group comments
| supporting analyses/models | E1300336 Repository for Signal Recycling Cavity Baffle Supporting Analyses/models | complete
T1300474 H1 SIGNAL RECYCLING CAVITY beam size_3-11-13
T1300798-v1_beam size at SR2 baffle
T1300421 Ghost Beam Scatter in Signal Recycling Cavity
T1300422 H1 Hartmann ITM Probe Scatter
T1300423 HAM Scraper Baffle Height
T1300424 Scattering Parameters Hartmann Beams
T1300426 SR3 and SR2 Baffles Hole Edge Scatter
T1300799-v1_SR3 HR BAFFLE CHARACTERISTICS
T1300800-v1_HAM SCRAPER BAF SPACER HEIGHT
T1300801-v1_SRM AR BAF SPACER HEIGHT
T1300803-v1_Signal recycling cavity beam parameters
T1300804-v1_SR Cavity Size Summary
T1300805-v1_Scattering from SRM AR Baf1_overlap integral
T1300806-v1_SR Cavity Baf scatter overlap_integral
T1300807-v1_HAM-BD heights
T1300808-v1_SR2 AR Baf_Hartmann Scraper Baf_revised sketch
T1300831-v1_SR2 Scraper Baffle sketch
| prototype tests | T1100053 FEA Testing of AOS SR2 Scrapper Baffle Concept | [11 empty] | 1 | 100%
| drawing/document tree/list |  | TBD | lisa/Nichole | 8 | 8 |  | 1 | 75%
| parts list (BOM) | E1300337 Repository for Signal Recycling Cavity Baffles BOM Docs
|  | E1200617 BOM SR2 SCRAPER BAFFLE CLAMPED ASSY, H1 | [7 empty] | 1 | 100%
|  | E1100053 BOM SR2 SCRAPER BAFFLE SKIN ASSEMBLY | [7 empty] | 1 | 100%
|  | E1100837 BOM HAM SCRAPER BAFFLE ASSEMBLY | [7 empty] | 1 | 100%
|  | E1100311 BOM FOR ALIGO SRM AR BAFFLE ASSEMBLY | [7 empty] | 1 | 100%
|  | E1100391 BOM FOR aLIGO SR3 BAFFLE ASSY | [7 empty] | 1 | 100%
| spares list |  | TBD | lisa/Nichole | 8 | 8 |  |  |  | 1 | 100%
| design drawings, schematics, interfaces, etc. | E1300350 Repository for Signal Recycling Cavity Baffles Design Drawings, Interfaces, etc. | TBD | Lisa/Eddie | 8 | 8
D1200922: aLIGO, AOS, SPACER, SR2 SCRAPPER BAFFLE ASSY, H1
D1101599: aLIGO AOS SR2 AR_HARTMANN BAFFLE ASSEMBLY
D1200141 aLIGO SRM AR BAFFLE ASSY
D1003205 ALIGO SR3 HR-AR BAFFLE ASSY
| SW Vault files | E1300356 Repository for Signal Recycling Cavity Baffles SW Vault Files | update TBD | Eddie | 16 | 16
D1200922: aLIGO, AOS, SPACER, SR2 SCRAPPER BAFFLE ASSY, H1
D1101599: aLIGO AOS SR2 AR_HARTMANN BAFFLE ASSEMBLY
D1200141 aLIGO SRM AR BAFFLE ASSY
D1003205 ALIGO SR3 HR-AR BAFFLE ASSY
| Specifications | See Common Documents
| Assembly procedure(s) | T1300340 SLC Signal Recycling Cavity Baffles Assembly and Installation | update TBD | Lisa | 8 | 8 | [5 empty] | 1 | 80%
| Installation plan/procedure(s) | E1100784 Initial Alignment Procedure -LHAM4 and LHAM5
D0900456 aLIGO Systems, HAM5-L1 Top Level Chamber Assembly
|  | T1300340 SLC Signal Recycling Cavity Baffles Assembly and Installation | see assy procedures
| Test & Commissioning Doc Tree |  | TBD | Jeff Lewis | 8 | 8 | [7 empty] | 1 | 0%
| Test plan/procedure(s) | E1101023 Signal Recycling Cavity Baffles Fabrication and Installation Test Plan | update TBD | Lisa | 4 | 4
| User Interface Software SVN | NA
| User's Manual(s) | NA
| Troubleshooting Guide | NA
| Safety Docs | E1100984 SLC Signal Recycling Cavity Baffle Install Hazard Analysis | done | [12 empty] | 1 | 100%
Signal Recycling Cavity Baffles Documents:
| acceptance document | E1300212 SLC Acceptance Documentation | TBD updated | Lisa | 8 | 8 | [7 empty] | 1 | 0%
| ICS inventory |  | TBD | Nichole | [5 empty] | 1 | 100%
| S-numbers |  | TBD | Nichole | 8 | 8
| Test results | E1300338 Repository for Signal Recycling Cavity Baffles Test Results
T1200457 aLIGO SRM AR Baffle - Modal Data
T1200391 Hartmann Baffle Modal Data (HAM Scraper Baffle)
T1200390 SR3 HR_H1-L1 Baffle Modal Data
T1200453 aLIGO SR3 AR L1-H1 Baffle Modal Testing
T1200505 SR2 Scraper Baffle Modal Testing
|  | E1300441 Install Signal Recycling Cavity Baffles LLO HAM4 Test | TBD | Vargas/Aidan | [9 empty] | 1 | 90%
|  | E1300392 Install Signal Recycling Cavity Baffles LLO HAM5 Test | TBD | Vargas | 4 | 4 | [7 empty] | 1 | 90%
|  | E1300393 Install Signal Recycling Cavity Baffles LHO HAM4 Test | TBD | Vo/Aidan | 4 | 4 | [7 empty] | 1 | 0%
|  | E1300394 Install Signal Recycling Cavity Baffles LHO HAM5 Test | TBD | Vo/Aidan | 4 | 4 | [7 empty] | 1 | 0%
| Channel/Signal List and Calibrations | NA
Viewports
| Final Design Document (FDD) | T1000746-v7_Viewports_Subsystem_FDD | TBD updated | Lisa | 16 | 16 |  | 1 | 90%
| final design report | E1300294 SLC & VP Design overview and detailed design documentation
| supporting analyses/models | T1200508 Aligo, WITNESS SAMPLES ILLUMINATION & VIDEO VPORT SELECTION , HAM3 L1-H1 | complete
| prototype tests | E1300270 aLIGO AOS SLC/VP Acceptance Directory
| drawing/document tree/list |  | TBD | lisa/Nichole | 8 | 8 |  | 1 | 75%
| parts list (BOM) | E1300335 Repository for Viewport BOM Docs
|  | E1300321 BOM Viewport Summary | [7 empty] | 1 | 100%
|  | E1100241 ISC Viewport Selection | [7 empty] | 1 | 100%
|  | E1100259 IO Viewports List | [7 empty] | 1 | 100%
|  | T1100292 Viewport Source List | [7 empty] | 1 | 100%
E1100479: Drawing Tree and BOM for D1100999 High Quality, 6", Non-Wedged, Viewport Assy
E1100480: Drawing Tree and BOM for D1101000 High Quality, 6", Wedged, Viewport Assy
| spares list |  | done | lisa/Nichole | [5 empty] | 1 | 100%
| design drawings, schematics, interfaces, etc. | E1300349 Repository for Viewports Design Drawings, Interfaces, etc. | update TBD | Lisa/Gleason | 16 | 16
D1101000: aLIGO, high quality, .75 deg wedged, 6" Viewport Assembly
D1100999-v4 aLIGO, high quality, non-wedged, 6in Viewport Assembly
D1101714-v3 ALIGO HIGH POWER WEDGED 6IN VIEWPORT ASSY
D1101670-v3 ALIGO HIGH POWER NON WEDGED 6IN VIEWPORT Assy
D1200963-v1_aLIGO_SLC_High Power Viewport Guard Assembly
D080367 VIEWPORT GUARD ASSEMBLY
D1101170-v1: ALIGO, VE, VIEWPORT GUARD ASSY., EXTENSION
D1101171 ALIGO, VE, VIEWPORT GUARD ASSY., MULTI-PIECE
D1101000: aLIGO, high quality, .75 deg wedged, 6" Viewport Assembly
| SW Vault files | E1300357 Repository for Viewport SW Vault Files | update TBD | Lisa/Gleason | 16 | 16
D1100999-v4 aLIGO, high quality, non-wedged, 6in Viewport Assembly
D1101714-v3 ALIGO HIGH POWER WEDGED 6IN VIEWPORT ASSY
D1101670-v3 ALIGO HIGH POWER NON WEDGED 6IN VIEWPORT Assy
D1200963-v1_aLIGO_SLC_High Power Viewport Guard Assembly
D080367 VIEWPORT GUARD ASSEMBLY
D1101170-v1: ALIGO, VE, VIEWPORT GUARD ASSY., EXTENSION
D1101171 ALIGO, VE, VIEWPORT GUARD ASSY., MULTI-PIECE
D1101000: aLIGO, high quality, .75 deg wedged, 6" Viewport Assembly
| Specifications | See Common Documents
E1300334 Repository for Viewport Repository for Viewport Specification Documents
E1000246 6.0 inch Vacuum Viewport Specification
E070124-A_septum window coating spec
E070069-v1 High Quality Window Polish
| Assembly procedure(s) | E1300328 Repository for Viewport Assembly Procedure Documents | [9 empty] | 1 | 100%
E000007-v2 VP cleaning procedure
D1100999 aLIGO, high quality, non-wedged, 6in Viewport Assy
D080367-v1_aLIGO_VE_Viewport Guard Assembly
D070107-A_e-LIGO_septum plate
D1001732_Septum_Viewport_Assy
D1101000 aLIGO, high quality, .75 deg wedged, 6" Viewport Assembly
E1100484-v7: Assembly Specification for the aLIGO, High Quality,Viewports
| Installation plan/procedure(s) | E1300333 Repository for Viewport Installation Procedure Documents | [9 empty] | 1 | 100%
E1000099 VP installation procedure
T1200255 H1 Temporary PRC Septum Plate Viewports As-Installed
T1200228 Viewport Installation locations LHO
D0901820 AdvLIGO VE HAM1-H1 Vacuum Equipment Assembly
D0901084 AdvLIGO VE HAM2-H1 Vacuum Equipment Assembly
D0901095 AdvLIGO VE HAM3-H1, Vacuum Equipment Assembly
D0901126 AdvLIGO VE HAM4-H1, Vacuum Equipment Assembly
D1201362 BSC Systems Level Supplementary Chamber-Level Build Documents
D0901823 AdvLIGO VE HAM6-H1 Vacuum Equipment Assembly
T1200253 H1 Input Septum Plate Port Viewports As-Installed
D0901143 AdvLIGO VE BSC2-H1, Vacuum Equipment Assembly
T1200211 NOTE ON ORIENTATION OF INPUT BEAM VIEWPORTS ON HAM 1 DOOR AND SEPTUM PLATE
T1200239 WHAM1 Viewports As-Installed
T1200245 WAMCA1 Viewports As-Installed
T1200246-v1: WAMCB1 Viewports As-Installed
D1201180 AdvLigo VE Input MC Tube WAMCA1-H1, Vacuum Equipment Assembly
D1201181 AdvLigo VE Input MC Tube WAMCB1-H1, Vacuum Equipment Assembly
D1201183 AdvLigo VE Output MC Tube WAMCB2-H1, Vacuum Equipment Assembly
T1200240-v3: WHAM2 Viewports As-Installed
T1200241-v2: WHAM3 Viewports As-Installed
T1200254-v1: H1 Output Septum Plate Port Viewports As-Installed
D1201179 AdvLigo VE H1, Y-Beam Mainfold. B-9B, A-1F, Vacuum Equipment Assembly
D1201178 AdvLigo VE H-1, X-Beam Manifold , B-9A, A-1C, Vacuum Equipment Assembly
D1201193 AdvLigo VE, H1, Y-End Manifold, Vacuum Equipment Assembly
D1201194 AdvLigo VE, H1, X-End Manifold, A-7A2, A-1E , Vacuum Equipment Assembly
D0901155 AdvLIGO VE BSC10-H1, Vacuum Equipment Assembly
D0901138 AdvLIGO VE BSC1-H1, Vacuum Equipment Assembly
D0901147 AdvLIGO VE BSC3-H1, Vacuum Equipment Assembly
T1200251-v1: H1 X-End Adapter A-1 WA-1E Viewports As-Installed
D1201182 AdvLigo VE Output MC Tube WAMCA2-H1, Vacuum Equipment Assembly
T1200234-v1: WBSC1 Viewports As-Installed
T1200235-v1: WBSC2 Viewports As-Installed
T1200236-v1: WBSC3 Viewports As-Installed
T1200237-v1: WBSC9 Viewports As-Installed
T1200238-v1: WBSC10 Viewports As-Installed
T1200242-v1: WHAM4 Viewports As-Installed
T1200243-v1: WHAM5 Viewports As-Installed
T1200247-v1: WAMCA2 Viewports As-Installed
T1200248-v1: WAMCB2 Viewports As-Installed
T1200250-v1: H1 H2 X-Beam Manifold Adapter A-1, WA-1C Viewports As-Installed
T1200252-v1: H1, H2 Y-Beam Manifold Adapter A-1, WA-1F Viewports As-Installed
T1200249-v1: H1 Y-End Adapter A-1 WA-1B Viewports As-Installed
D0901130 AdvLIGO VE HAM5-H1, Vacuum Equipment Assembly
T1300202 aLIGO GigE camera layout and usage
D0901151 AdvLIGO VE BSC9-H1, Vacuum Equipment Assembly
D1001662-v2 H1 L1 Output Septum Plate Port Locations
| Test & Commissioning Doc Tree |  | TBD | Jeff Lewis | 8 | 8 | [7 empty] | 1 | 0%
Test plan/procedure(s)
|  | E1100948-v6 Viewport Inspection and Testing | update TBD | Jeff Lewis | 8 | 8
| User Interface Software SVN | NA
| User's Manual(s) | NA
| Troubleshooting Guide | NA
| Safety Docs | E1100246 Viewport Hazard Analysis | update TBD | Lisa | 8 | 8 | [9 empty] | 1 | 75%
Viewport Documents:
| acceptance document | E1300212 SLC Acceptance Documentation | update TBD | Jeff Lewis | 16 | 16 | [7 empty] | 1 | 75%
| ICS inventory | [8 empty] | 1 | 100%
| S-numbers |  | TBD | Nichole | 8 | 8
| Test results | E1300438 Repository for Viewport Test Results
|  | E1300447 TEST-VP | ongoing | DeRenzis | 16 | 16 | [7 empty] | 1 | 90%
|  | E1200445 LLO Viewport Assembly Status | done | [10 empty] | 1 | 100%
M080310-00 Safety Bulletin: Kovar-Sealed Glass Vacuum Viewports
|  | T1200553 Viewport AR Coating Measurement | done | [10 empty] | 1 | 100%
|  | T1300531 Wedge Viewport 500ppm D1101005-v1 E070124-v1 AR Coating Measurement | done | [10 empty] | 1 | 100%
|  | Leak Test & Overpressure Test document | TBD | Jeff Lewis | 8 | 8 | [7 empty] | 1 | 0%
| Channel/Signal List and Calibrations | NA
|  | Acceptance Doc subtotal hours |  |  | 1108 | 1088 | 8 | 18 | 1505% | 29 | 2750% | 15 | 1360% | 55 | 2390% | 8 | 675%
|  | % completion | [6 empty] | 83.61% |  | 94.83% |  | 90.67% |  | 43.45% |  | 84.38%