## SUS
TITLE | 3rd IFO Long Term Storage Acceptance and Punchlist
DATE | 1st April 2015
SUB SYSTEM | SUS
RESP PERSON(s) | Betsy Weaver | Norna Robertson
RELEVANT DOCS
ACCEPTANCE
ITEM NUMBER | ITEM | DEFINITION | COMMENTS | DCC NUMBERS / ICS LINK | STATUS (NOTES) | SIGNED OFF 3rd IFO | DATE
1 | STORAGE PLAN REVIEW | Long Term Storage Requirements and Procedures are up to date. | For grouping of all Subsytem Storage Requirements Documents updated (see E1300001 ) | SUS Storage plan is LIGO-T1200527 | DONE | Norna Robertson
2 | BOM REVIEW | Types and quantities of parts/assemblies/spares/tooling to be received by LTS are clearly understood. | Coordinate with LTS lead | D1500108 | DONE | Jodi Fauver | Dec 19th 2015
3 | CROSS CHECK | All Hardware (parts/assemblies/spares/tooling) checked into LAM. All in-vacuum parts have correct ICS information. | LAM=Long-Term Storage Asset Management (aka barcode system) | D1500108 | DONE | Jodi Fauver | Dec 19th 2015
T1500107
4 | BOM RECEIVED | All assemblies/spares listed in BOM have been delivered to LTS custody. LTS lead has physical or virtual control of assemblies/spares. | Virtual custody means that any hardware still in use is checked into LAM/ICS for 3IFO but is checked out to responsible owner. | T1500107 | DONE | Jodi Fauver | Dec 19th 2015
5 | STORAGE VERIFICATION | Verification that Hardware is stored according to aLIGO and relevant substystem LTS plans. |  | Refer to T1500107 |  | Jodi Fauver
PUNCHLIST
ITEM NUMBER | DESCRIPTION | STATUS | VENDOR | RESP PERSON @ LHO | BUYER | DUE DATE | ADDITIONAL NOTES
1 | Out for machine QTY 1 D1300956 | Wire shielding baffle for 3IFO, and then 2 for spare, will separate SUS/OPS | Shop Paid | Betsy | Betsy | 2015-04-03
ITEMS STORED WITH NOTES/DEFECTS

## IAS
DATE | 3rd IFO Long Term Storage Acceptance and Punchlist
DATE | 1st April 2015
SUB SYSTEM | IAS
RESP PERSON(s) | Doug Cook
RELEVANT DOCS
ACCEPTANCE
ITEM NUMBER | ITEM | DEFINITION | COMMENTS | DCC NUMBERS | STATUS (NOTES) | SIGNED OFF 3rd IFO | DATE
1 | STORAGE PLAN REVIEW | Long Term Storage Requirements and Procedures are up to date. | For grouping of all Subsytem Storage Requirements Documents updated (see E1300001 ) | T1300011 | DONE | Jodi Fauver | Dec 19th 2015
2 | BOM REVIEW | Types and quantities of parts/assemblies/spares/tooling to be received by LTS are clearly understood.1 ea of items on E1500160 and E1500162 | Coordinate with LTS lead | E1200485 AOS IAS - Initial Alignment Document Tree (Index)
E1500160 IAS Alignment List of Irises for PR3 and SR3
E1500162 IAS Alignment List of Targets used for SUS components
3 | CROSS CHECK | All Hardware (parts/assemblies/spares/tooling) checked into LAM. All in-vacuum parts have correct ICS information. | LAM=Long-Term Storage Asset Management (aka barcode system) | T1500137 | DONE
4 | BOM RECEIVED | All assemblies/spares listed in BOM have been delivered to LTS custody. LTS lead has physical or virtual control of assemblies/spares. | Virtual custody means that any hardware still in use is checked into LAM/ICS for 3IFO but is checked out to responsible owner. | Refer to T1500137 | DONE
E1200485 AOS IAS - Initial Alignment Document Tree (Index)
E1500160 IAS Alignment List of Irises for PR3 and SR3
E1500162 IAS Alignment List of Targets used for SUS components
T1500087 optosigma orders for 3IFO components
5 | STORAGE VERIFICATION | Verification that Hardware is stored according to aLIGO and relevant substystem LTS plans. |  | T1500132
PUNCHLIST
ITEM NUMBER | DESCRIPTION | STATUS | VENDOR | RESP PERSON @ LHO | BUYER | DUE DATE | ADDITIONAL NOTES

## OpLev
TITLE | 3rd IFO Long Term Storage Acceptance and Punchlist
DATE | 1st April 2015
SUB SYSTEM | Op Lev
RESP PERSON(s) | Doug Cook / Eric Gustafson
RELEVANT DOCS
ACCEPTANCE
ITEM NUMBER | ITEM | DEFINITION | COMMENTS | DCC NUMBERS / ICS LINK | STATUS (NOTES) | SIGNED OFF 3rd IFO | DATE
1 | STORAGE PLAN REVIEW | Long Term Storage Requirements and Procedures are up to date. | For grouping of all Subsytem Storage Requirements Documents updated (see E1300001 ) | Op Lev Storage plan LIGO-T1200558 | DONE | Jodi Fauver | 30th Oct 2014
2 | BOM REVIEW | Types and quantities of parts/assemblies/spares/tooling to be received by LTS are clearly understood. | Coordinate with LTS lead | T1500081 | DONE | Jodi Fauver | 20th June 2014
3 | CROSS CHECK | All Hardware (parts/assemblies/spares/tooling) checked into LAM. All in-vacuum parts have correct ICS information. | LAM=Long-Term Storage Asset Management (aka barcode system) | T1500081 | DONE | Jodi Fauver | 20th June 2014
T1500108
4 | BOM RECEIVED | All assemblies/spares listed in BOM have been delivered to LTS custody. LTS lead has physical or virtual control of assemblies/spares. | Virtual custody means that any hardware still in use is checked into LAM/ICS for 3IFO but is checked out to responsible owner. | T1500108 | DONE | Jodi Fauver | 20th June 2014
5 | STORAGE VERIFICATION | Verification that Hardware is stored according to aLIGO and relevant substystem LTS plans. |  | Refer to T1500108 | DONE | Jodi Fauver | 18th Dec 2014
PUNCHLIST
ITEM NUMBER | DESCRIPTION | STATUS | VENDOR | RESP PERSON @ LHO | BUYER | DUE DATE | ADDITIONAL NOTES
1 | OptoSigma 70mm Pitch-Yaw Adapter Plate | DONE | Opto Sigma | Doug | Steve M CALTECH |  |  | 4 ea | received
2 | 10m fiber for Laser | DONE |  | Doug | Doug |  |  |  | received
3 | D1100290 QPD Amplifier Board Assembly | DONE |  | Doug | Gary McIntire |  |  |  | received
4 | D1100342 Receiver Enclosure Assmbly (Left Hand) | DONE |  | Doug has ordered | Doug |  |  | 3 ea | received
5 | Projection Telescope Assembly, Long | DONE |  | Doug | Doug
1 | PCB Carrier (Made from Sigma SGx33-M6) | minor modifications needed. Will be stored with defect record. | Brockmans machine shop | Doug | Doug | received - left on until inventory into 3rd IFO complete |  | 4 ea
7 | Base Extension | DONE |  | Doug has ordered | Doug | received |  | 1 ea
2 | Giraffe Clamp Plate | Ordered | Brockmans machine shop | Doug has ordered | Doug/Jodi | received - left on until inventory into 3rd IFO complete |  | 8 ea
9 | Gortiflex 4" Rubber Bellows | DONE |  | Gary | Jodi | received
10 | Gortiflex 6" Rubber Bellows | DONE |  | Gary | Jodi | received
3 | 3" Optical Post | Ordered | Brockmans machine shop | Doug | Doug | received - left on until inventory into 3rd IFO complete |  | 4 ea
12 | HAM Table Fork | DONE |  | Doug | Doug |  |  | 4 ea
13 | DC/DC Power Supply aka Converter Boards | DONE |  |  | Doug | received
4 | Custom Laser Cable (11ea) with power supply | Fil ordering/assembling 11 for 3IFO - complete | LHO | Doug and Fil | Filiberto | received - left on until inventory into 3rd IFO complete |  | 11 ea
| Opto Sigma X & Y Translation Stages | DONE | Opto Sigma | Doug | Steve M CALTECH |  |  | 4 ea | received
| Opto Sigma X & Y Translation Stage Controller | DONE | Opto Sigma | Doug | Steve M CALTECH |  |  | 1 ea | received

## PCal
TITLE | 3rd IFO Long Term Storage Acceptance and Punchlist
DATE | 1st April 2015
SUB SYSTEM | PCal
RESP PERSON(s) | Rick
RELEVANT DOCS
ACCEPTANCE
ITEM NUMBER | ITEM | DEFINITION | COMMENTS | DCC NUMBERS / ICS LINK | STATUS (NOTES) | SIGNED OFF 3rd IFO | DATE
1 | STORAGE PLAN REVIEW | Long Term Storage Requirements and Procedures are up to date. | For grouping of all Subsytem Storage Requirements Documents updated (see E1300001 ) | LIGO-T1300012: Photon Calibrator (PhCal) Long Term Storage for the 3rd aLIGO Interferometer | DONE | Gary Davis | 30th Oct 2014
2 | BOM REVIEW | Types and quantities of parts/assemblies/spares/tooling to be received by LTS are clearly understood. | Coordinate with LTS lead | T1400295 | DONE | Jodi Fauver, Gary Davis | 20th June 2014
3 | CROSS CHECK | All Hardware (parts/assemblies/spares/tooling) checked into LAM. All in-vacuum parts have correct ICS information. | LAM=Long-Term Storage Asset Management (aka barcode system) | T1400295 |  | Gary Davis
T1500109
4 | BOM RECEIVED | All assemblies/spares listed in BOM have been delivered to LTS custody. LTS lead has physical or virtual control of assemblies/spares. | Virtual custody means that any hardware still in use is checked into LAM/ICS for 3IFO but is checked out to responsible owner. | T1400295 | DONE | Jodi Fauver, Gary Davis | 20th June 2014
T1500109
5 | STORAGE VERIFICATION | Verification that Hardware is stored according to aLIGO and relevant substystem LTS plans. |  | T1400295 |  | Gary Davis
PUNCHLIST
ITEM NUMBER | DESCRIPTION | STATUS | VENDOR | RESP PERSON @ LHO | BUYER | DUE DATE | ADDITIONAL NOTES
ITEMS STORED WITH NOTES/DEFECTS
1 | Put Viewport "MickeyMouse" targets back into 3rd ifo storage (change to check out from LAM) |  |  | Jodi |  | 2015-04-01 | Make sure this is on the check out list-Jodi
2 | Assemble ITM camera housings, box, and deliver for storage |  | RDL and Magic Metals | Rick or Nutsinee |  | 2015-05-01
3 | Add ETM camera upgrade hardware (tamaron lenses, spacers and hardware) into the 3rd. ifo storage |  | B&H camera | Rick or Nutsinee |  | 2015-04-15 | RS Done
4 | Add two AOMs to Tx module inventory in case existing ones are damaged by too much RF power. |  |  | Rick |  |  | RS Done
5 | Add two BNC to DB-9 electronics modules to inventory (awaiting delivery from Ben Abbott) |  | CIT Ben Abbott | Rick (from Ben) |  | 2015-04-15
6 | Add heat sink personnel protectors to inventory |  | Magic Metals | Rick (with help from JoeG) |  | 2015-04-05
7 | Add two viewports to inventory when they arrive (after March 31). |  | MDL | Rick |  | 2015-05-15
8 | Add two AOM polarizer hardware "kits" to 3rd. ifo storage |  |  | Rick |  | 2015-04-15 | RS Done

## SLC
TITLE | 3rd IFO Long Term Storage Acceptance and Punchlist
DATE | 1st April 2015
SUB SYSTEM | SLC
RESP PERSON(s) | Mitch Robinson
RELEVANT DOCS
ACCEPTANCE
ITEM NUMBER | ITEM | DEFINITION | COMMENTS | DCC NUMBERS | STATUS (NOTES) | SIGNED OFF 3rd IFO | DATE
1 | STORAGE PLAN REVIEW | Long Term Storage Requirements and Procedures are up to date. | For grouping of all Subsytem Storage Requirements Documents updated (see E1300001 ) | T1300006 | DONE | Jodi Fauver
2 | BOM REVIEW | Types and quantities of parts/assemblies/spares/tooling to be received by LTS are clearly understood. | Coordinate with LTS lead | T1500112 | DONE | Jodi Fauver | 20th June 2014
3 | CROSS CHECK | All Hardware (parts/assemblies/spares/tooling) checked into LAM. All in-vacuum parts have correct ICS information. | LAM=Long-Term Storage Asset Management (aka barcode system) | T1500106 | DONE | Jodi Fauver | 20th June 2014
4 | BOM RECEIVED | All assemblies/spares listed in BOM have been delivered to LTS custody. LTS lead has physical or virtual control of assemblies/spares. | Virtual custody means that any hardware still in use is checked into LAM/ICS for 3IFO but is checked out to responsible owner. | T1500106 | DONE | Jodi Fauver | 20th June 2014
5 | STORAGE VERIFICATION | Verification that Hardware is stored according to aLIGO and relevant substystem LTS plans. |  | T1500106 | DONE | Jodi Fauver | 18th Dec 2014
PUNCHLIST
ITEM NUMBER | DESCRIPTION | STATUS | VENDOR | RESP PERSON @ LHO | BUYER | DUE DATE | ADDITIONAL NOTES
1 | ACB Photodiodes and ACB cable. | Stored at LHO. | CIT | Calum
1 | 5 Machine parts on order | Parts on order | RDL, TK, Cannon (all paid) | Mitchell, Betsy | Betsy | 3/27/15 - 4/15/15
ITEMS STORED WITH NOTES/DEFECTS
1 | Arm Cavity Baffle aka The W | Stored at LHO with rust |  |  |  | This is stored as a defect record.
2 | Mouse hole covers (2 of each of the 4 types: D1201160, D1201163, D1201164, D1201165) | Material ship to CIT | CIT | Mitch / (Calum) |  | Material for mouse hole covers is stored. Machining and subsequent oxidation is required. This is stored as a defect record. | Jodi to send oxidized material to Calum.

## TCS
TITLE | 3rd IFO Long Term Storage Acceptance and Punchlist
DATE | 1st April 2015
SUB SYSTEM | TCS
RESP PERSON(s) | Aidan Brooks
RELEVANT DOCS
ACCEPTANCE
ITEM NUMBER | ITEM | DEFINITION | COMMENTS | DCC NUMBERS / ICS | STATUS (NOTES) | SIGNED OFF 3rd IFO | DATE
1 | STORAGE PLAN REVIEW | Long Term Storage Requirements and Procedures are up to date. | For grouping of all Subsytem Storage Requirements Documents updated (see E1300001 ) | "TCS LTS plan" T1300003 |  | Jodi
2 | BOM REVIEW | Types and quantities of parts/assemblies/spares/tooling to be received by LTS are clearly understood. | Coordinate with LTS lead | RH BOM: E1500060 |  | Jodi
|  |  |  | HWS BOM: E1500058 |  | Jodi
|  |  |  | CO2 BOM: E1500059 |  | Jodi
3 | CROSS CHECK | All Hardware (parts/assemblies/spares/tooling) checked into LAM. All in-vacuum parts have correct ICS information. | LAM=Long-Term Storage Asset Management (aka barcode system) | TCS HWS T1500111
4 | BOM RECEIVED | All assemblies/spares listed in BOM have been delivered to LTS custody. LTS lead has physical or virtual control of assemblies/spares. | Virtual custody means that any hardware still in use is checked into LAM/ICS for 3IFO but is checked out to responsible owner. | N/A
5 | STORAGE VERIFICATION | Verification that Hardware is stored according to aLIGO and relevant substystem LTS plans. |  | N/A | Jodi?
PUNCHLIST
ITEM NUMBER | DESCRIPTION | STATUS | VENDOR | RESP PERSON @ LHO | BUYER | DUE DATE | ADDITIONAL NOTES
ITEMS STORED WITH NOTES/DEFECTS
STORED AT CIT | DCBS for HWS | Ordered placed last week of Feb | Precision Photonics | Greg Grabeel | Dennis Coyne | 2015-03-23 | Arrived at CIT 26-Mar | UPS tracking: 1Z406YV20399709502
DONE | HWS power D1102206 | Need to confirm these are stored at LHO in sufficient quantity |  | Richard McCarthy |  |  | Richard is checking this
DONE | Phoenix Contact for safety shut off | Not ordered. At LHO? |  | Greg Grabeel | Aidan Brooks |  | Richard is checking this
STORED AT CIT | Laser controller chassis | At CIT waiting for replacement front panel | LIGO | Greg Grabeel | Aidan Brooks | 2015-03-25 | Waiting for front panel to arrive to ship to LHO
STORED AT CIT | HWS plate RTD sensors | Need to be shipped to LHO | LIGO | Greg Grabeel | Aidan Brooks | 2015-03-25 | Waiting to be shipped to LHO
STORED AT CIT | CO2 Photodiodes | Need to be shipped to LHO |  |  | Alastair | 2015-03-25 | Waiting to be shipped to LHO
DONE | Laser - 50W | At CIT - where to store? |  |  |  |  | Deemed stored at CIT. Stays here until end of first observing run for Commissioning Suport
DONE | Viewport clamp - D1102396 | Not ordered. Can we use D1101002? | LIGO | Greg Grabeel | Aidan Brooks |  | About $700 ea. (I think we worked this out last week???)
Richard is checking this
NOTED | HWS in-vacuum hardware (screws/washers) | stored, not cleaned | UC Components | Greg Grabeel | Aidan Brooks |  | TCS HWS 3IFO Box 13
NOTED | RH in-vacuum hardware | stored, not cleaned |  |  |  |  | TCS RH 3IFO Box 2 (20-24 AWG gold pins, C-812, FA-404)
NOTED | HWS Assy parts | D1000658-v2. HWS Clamp. To be shipped | LIGO | Greg Grabeel | Aidan Brooks |  | Shipping 1x -v2, 1x -v3, functional but lacking ergonomic changes that -v5 has
|  | D1000708-v2 - HWS spacer. To be shipped | LIGO | Greg Grabeel | Aidan Brooks |  | Shipping 1x -v2, 1x -v3, functional but lacking ergonomic changes that -v7 has
NOTED | Laser controller chassis needs front panel replaced
NOTED | Photodiodes need assembly

## TMS
TITLE | 3rd IFO Long Term Storage Acceptance and Punchlist
DATE | 1st April 2015
SUB SYSTEM | TMS
RESP PERSON(s) | Jodi / (Calum)
RELEVANT DOCS
ACCEPTANCE
ITEM NUMBER | ITEM | DEFINITION | COMMENTS | DCC NUMBERS / ICS | STATUS (NOTES) | SIGNED OFF 3rd IFO | DATE
1 | STORAGE PLAN REVIEW | Long Term Storage Requirements and Procedures are up to date. | For grouping of all Subsytem Storage Requirements Documents updated (see E1300001 ) | LIGO-T1300007: Transmission Monitor Suspension (TMS) Long Term Storage (LTS) for the 3rd IFO and LIGO LTS | DONE | Calum Torrie
2 | BOM REVIEW | Types and quantities of parts/assemblies/spares/tooling to be received by LTS are clearly understood. | Coordinate with LTS lead | G1300422 Pg 33 | DONE | Jodi Fauver | 20th June 2014
18th March 2015
3 | CROSS CHECK | All Hardware (parts/assemblies/spares/tooling) checked into LAM. All in-vacuum parts have correct ICS information. | LAM=Long-Term Storage Asset Management (aka barcode system) | T1500103-v1 | DONE | Jodi Fauver | 20th June 2014
4 | BOM RECEIVED | All assemblies/spares listed in BOM have been delivered to LTS custody. LTS lead has physical or virtual control of assemblies/spares. | Virtual custody means that any hardware still in use is checked into LAM/ICS for 3IFO but is checked out to responsible owner. | T1500103-v1 | DONE | Jodi Fauver | 20th June 2014
5 | STORAGE VERIFICATION | Verification that Hardware is stored according to aLIGO and relevant substystem LTS plans. |  | See Doc T1500103 | DONE | Jodi Fauver | 18th Dec 2014
PUNCHLIST
ITEM NUMBER | DESCRIPTION | STATUS | VENDOR | RESP PERSON @ LHO | BUYER | DUE DATE | ADDITIONAL NOTES
2 | Look up LTS of TMS |  |  | Calum

## Viewports
TITLE | 3rd IFO Long Term Storage Acceptance and Punchlist
DATE | 1st April 2015
SUB SYSTEM | VIEWPORTS
RESP PERSON(s) | Joe
RELEVANT DOCS
ACCEPTANCE
ITEM NUMBER | ITEM | DEFINITION | COMMENTS | DCC NUMBERS / ICS | STATUS (NOTES) | SIGNED OFF 3rd IFO | DATE
1 | STORAGE PLAN REVIEW | Long Term Storage Requirements and Procedures are up to date. | For grouping of all Subsytem Storage Requirements Documents updated (see E1300001 ) | E1400073 | DONE | Calum Torrie | 2014-10-28
2 | BOM REVIEW | Types and quantities of parts/assemblies/spares/tooling to be received by LTS are clearly understood. | Coordinate with LTS lead | https://dcc.ligo.org/T1500105-v1. Also refer to ICS storage loads Storage Loads 7737, 7738, 7741, 7750. | DONE | Jodi Fauver | 18th Dec 2014
3 | CROSS CHECK | All Hardware (parts/assemblies/spares/tooling) checked into LAM. All in-vacuum parts have correct ICS information. | LAM=Long-Term Storage Asset Management (aka barcode system) | T1500135 | DONE | Jodi Fauver | 18th Dec 2014
4 | BOM RECEIVED | All assemblies/spares listed in BOM have been delivered to LTS custody. LTS lead has physical or virtual control of assemblies/spares. | Virtual custody means that any hardware still in use is checked into LAM/ICS for 3IFO but is checked out to responsible owner. | T1500135 | DONE | Jodi Fauver | 18th Dec 2014
5 | STORAGE VERIFICATION | Verification that Hardware is stored according to aLIGO and relevant substystem LTS plans. |  | Refer to T1500135 | DONE | Jodi Fauver | 18th Dec 2014
PUNCHLIST
ITEM NUMBER | DESCRIPTION | STATUS | VENDOR | RESP PERSON @ LHO | BUYER | DUE DATE | ADDITIONAL NOTES
1 | 9722012, 7.8" commercial VP | on order, qty 15 | MDC | Joe | Calum | 2015-04-20 | Will begin processing upon arrival.
2 | C-3120-A, 5/16 X 1.25 vented Ag-plated SHCS | ordered, qty 100 | UCC | Joe | Gary | Rcv'd 4/1/2015 | Left in for transfer to 3rd IFO
3 | C-1628-A, 3/8-16 X 1.75 vented SHCS | ordered, qty 100 | UCC | Joe | Gary | Rcv'd 4/1/2015 | Left in for transfer to 3rd IFO
4 | C-3114-A, 5/16-24 X .875 vented Ag-plated SHCS | ordered, qty24 | UCC | Joe | Gary | Rcv'd 4/1/2015 | Left in for transfer to 3rd IFO
5 | Pack and Store |  |  | Jodi Fauver, Gary Davis
6 | ICS Update |  |  | Jodi Fauver, Gary Davis
7 | LAM Update |  |  | Jodi Fauver, Gary Davis
8 | Storage Loads 7737, 7738, 7741, 7750 | Completed |  | Joe |  |  | Will do one more storage load when the remaining VPs are processed.

## COC
TITLE | 3rd IFO Long Term Storage Acceptance and Punchlist
DATE | 1st April 2015
SUB SYSTEM | COC
RESP PERSON(s) | Jodi / (GariLynn)
RELEVANT DOCS
ACCEPTANCE
ITEM NUMBER | ITEM | DEFINITION | COMMENTS | DCC NUMBERS / ICS | STATUS (NOTES) | SIGNED OFF 3rd IFO | DATE
1 | STORAGE PLAN REVIEW | Long Term Storage Requirements and Procedures are up to date. | For grouping of all Subsytem Storage Requirements Documents updated (see E1300001 ) | T1300016 | DONE | GariLynn Billingsley
2 | BOM REVIEW | Types and quantities of parts/assemblies/spares/tooling to be received by LTS are clearly understood. | Coordinate with LTS lead | T1500104 | DONE | Jodi Fauver | 18th Dec 2014
3 | CROSS CHECK | All Hardware (parts/assemblies/spares/tooling) checked into LAM. All in-vacuum parts have correct ICS information. | LAM=Long-Term Storage Asset Management (aka barcode system) | T1500110
4 | BOM RECEIVED | All assemblies/spares listed in BOM have been delivered to LTS custody. LTS lead has physical or virtual control of assemblies/spares. | Virtual custody means that any hardware still in use is checked into LAM/ICS for 3IFO but is checked out to responsible owner. | T1500110
5 | STORAGE VERIFICATION | Verification that Hardware is stored according to aLIGO and relevant substystem LTS plans. |  | Refer to 1500110 | Off-site storage at Caltech. | Jodi Fauver
PUNCHLIST
ITEM NUMBER | DESCRIPTION | STATUS | VENDOR | RESP PERSON @ LHO | BUYER | DUE DATE | ADDITIONAL NOTES

## DAQ
TITLE | 3rd IFO Long Term Storage Acceptance and Punchlist
DATE | 1st April 2015
SUB SYSTEM | DAQ
RESP PERSON(s) | Jodi / (Rolf)
RELEVANT DOCS
ACCEPTANCE
ITEM NUMBER | ITEM | DEFINITION | COMMENTS | DCC NUMBERS / ICS | STATUS (NOTES) | SIGNED OFF 3rd IFO | DATE
1 | STORAGE PLAN REVIEW | Long Term Storage Requirements and Procedures are up to date. | For grouping of all Subsytem Storage Requirements Documents updated (see E1300001 ) | LIGO-T1300002 | DONE | Jodi Fauver | 2014-05-01
2 | BOM REVIEW | Types and quantities of parts/assemblies/spares/tooling to be received by LTS are clearly understood. | Coordinate with LTS lead | LIGO-T1300835 | DONE | Jodi Fauver | 2014-05-02
3 | CROSS CHECK | All Hardware (parts/assemblies/spares/tooling) checked into LAM. All in-vacuum parts have correct ICS information. | LAM=Long-Term Storage Asset Management (aka barcode system) | LIGO-M1300493 | DONE | Jodi Fauver | 2014-05-03
4 | BOM RECEIVED | All assemblies/spares listed in BOM have been delivered to LTS custody. LTS lead has physical or virtual control of assemblies/spares. | Virtual custody means that any hardware still in use is checked into LAM/ICS for 3IFO but is checked out to responsible owner. | Refer to M1300493 (5 items in virtual custody) | DONE | Jodi Fauver | 2014-05-04
5 | STORAGE VERIFICATION | Verification that Hardware is stored according to aLIGO and relevant substystem LTS plans. |  | Covered in plastic with desiccant and HIC: pix may be viewed on M1300493 | TO DO | Jodi Fauver | 2014-05-05
PUNCHLIST
ITEM NUMBER | DESCRIPTION | STATUS | VENDOR | RESP PERSON @ LHO | BUYER | DUE DATE | ADDITIONAL NOTES
1 | Place LAM tag on black Master Timing Fanout unit | This will be completed on Ops. (part of LTS.) |  | JF |  |  | ASAP
2 | Redo bags and desiccant | This will be completed on Ops. (part of LTS.) |  | JF |  |  | (171212-303-403-404-504)
3 | SEI Chasis checked out by Ops for use | Currently stored at CIT, LHO and LLO. Serial numbers have been provided and this items stays in as reminder of these items have been checked out. |  | Filliberto at LHO. Ben at CIT and Carl at LLO. Serial numbers are with Jodi and will be recorded in LAM system. |  |  | ASAP
Order more bags

## INSFMP
TITLE | 3rd IFO Long Term Storage Acceptance and Punchlist
DATE | 1st April 2015
SUB SYSTEM | FMP
RESP PERSON(s) | Travis / Calum
RELEVANT DOCS
ACCEPTANCE
ITEM NUMBER | ITEM | DEFINITION | COMMENTS | DCC NUMBERS / ICS | STATUS (NOTES) | SIGNED OFF 3rd IFO | DATE
1 | STORAGE PLAN REVIEW | Long Term Storage Requirements and Procedures are up to date. | For grouping of all Subsytem Storage Requirements Documents updated (see E1300001 ) | T1300010 | DONE | John Worden
2 | BOM REVIEW | Types and quantities of parts/assemblies/spares/tooling to be received by LTS are clearly understood. | Coordinate with LTS lead | T1200222 | DONE | Jodi Fauver | 18th Dec 2014
T1300010
3 | CROSS CHECK | All Hardware (parts/assemblies/spares/tooling) checked into LAM. All in-vacuum parts have correct ICS information. | LAM=Long-Term Storage Asset Management (aka barcode system) | T1500128 | DONE | Jodi Fauver | 18th Dec 2014
4 | BOM RECEIVED | All assemblies/spares listed in BOM have been delivered to LTS custody. LTS lead has physical or virtual control of assemblies/spares. | Virtual custody means that any hardware still in use is checked into LAM/ICS for 3IFO but is checked out to responsible owner. | Refer to T1500128 | DONE | Jodi Fauver | 18th Dec 2014
5 | STORAGE VERIFICATION | Verification that Hardware is stored according to aLIGO and relevant substystem LTS plans. |  | Refer to T1500128 | DONE | Jodi Fauver | 18th Dec 2014 | Not sure how this can be considered done?
PUNCHLIST
ITEM NUMBER | DESCRIPTION | STATUS | VENDOR | RESP PERSON @ LHO | BUYER | DUE DATE | ADDITIONAL NOTES
ITEMS STORED WITH NOTES/DEFECTS
1 | 1 HAM lift D1001664 | Being stored at LLO. |  | Jodi to tag when at LLO
OPS RELATED
1 | N2 Purge | All SEI and SUS storage containers need to be checked for gas supply & Communication from N2 purge to control room |  | Bubba
2 | BSC5 -Move to final location in LVEA | The soonest this will happen is 07 April 2015. (repeat from SEI list) |  | Bubba, Jodi
3 | HAM Passive Stack | Needs to be moved to final location (repeat from sei list.) |  | Hugh, Jodi
4 | HEPI (off-site) | Need to move HEPI from off-site to LHO location. |  | Jodi
5 | Dessicant cabinet | Needs to be moved to LVEA (and hooked to Nitrogen purge) |  | Jodi, Jeff
6 | H2 HEPI | Needs to be deinstalled |  | Jodi
7 | HEPI Actuators | Flush/cycle on Regular basis |  | Jodi
8 | Clean and Bake | Various |  | Jodi
9 | Audit conditions and quantities | As outlined in the general storage plan |  | Jodi
10 | Electronics racks | Need to be bagged, tagged, have desiccant and humidity indicator cards added.

## IO
TITLE | 3rd IFO Long Term Storage Acceptance and Punchlist
DATE | 1st April 2015
SUB SYSTEM | IO
RESP PERSON(s) | Matt H
RELEVANT DOCS | T1200567 & T1500097 & T1500117
ACCEPTANCE
ITEM NUMBER | ITEM | DEFINITION | COMMENTS | DCC NUMBERS / ICS | STATUS (NOTES) | SIGNED OFF 3rd IFO | DATE
1 | STORAGE PLAN REVIEW | Long Term Storage Requirements and Procedures are up to date. | For grouping of all Subsytem Storage Requirements Documents updated (see E1300001 ) | T1200567
2 | BOM REVIEW | Types and quantities of parts/assemblies/spares/tooling to be received by LTS are clearly understood. | Coordinate with LTS lead | T1500097
3 | CROSS CHECK | All Hardware (parts/assemblies/spares/tooling) checked into LAM. All in-vacuum parts have correct ICS information. | LAM=Long-Term Storage Asset Management (aka barcode system) | Doing ICS (Storage load 7739) where can but inventory can be found in T1500097 main document spreadsheet (not S/N's though of parts) |  | Jodi to confirm
T1500124
4 | BOM RECEIVED | All assemblies/spares listed in BOM have been delivered to LTS custody. LTS lead has physical or virtual control of assemblies/spares. | Virtual custody means that any hardware still in use is checked into LAM/ICS for 3IFO but is checked out to responsible owner. | T1500124 |  | Jodi to confirm
5 | STORAGE VERIFICATION | Verification that Hardware is stored according to aLIGO and relevant substystem LTS plans. |  |  |  | Jodi to confirm
PUNCHLIST
ITEM NUMBER | DESCRIPTION | STATUS | VENDOR | RESP PERSON @ LHO | BUYER | DUE DATE | ADDITIONAL NOTES
1 | 13 different types of machined parts (of varying quatitites) | Ordered and being machined. OPS to C&B and then be stored away (see T1500097 3rd IFO order tracking for storage locations) | TK, Cannon, RDL | Betsy/Jodi if arrvies after Matt leaves | Betsy | 2015-04-15 | T1500097
2 | RF Photodiode | ordered. | Newport | Jodi (if arrives after Matt gone) | Jodi/Gary | 2015-05-04 | T1500097
3 | 1" lens for ISS array (E1200433 type 1) | Matt to ship to LHO once he is back at LLO as should be two still stored away/hidden (one for LLO one for 3rd IFO) |  | Jodi |  | ~April 6 2015 | T1500097
4 | PZT | PZT ordered | Physik Instrumente | Jodi (if arrives after Matt gone) | Jodi/Gary | 4-5 weeks (from Mar 13) so approx 4/20/2015 | T1500097
5 | PZT Controller | Jodi checked out & sent for calibration 3/25 - Jodi trying to stop | PI | Jodi |  | April 2nd 2015. | It is headed back.
ITEMS STORED WITH NOTES/DEFECTS
1 | Optic holder press fit magnets | Arrived and with Jodi. OPS to C&B and then be stored away (see T1500097 for storage location) | UF | Jodi | Guido/Giacomo | Mid April 2015 | T1500097
2 | Items not supplied by UF that are to be obtained by India | See list on T1500097 (really should have been on M1300534) |  |  |  |  | T1500097

## ISC
TITLE | 3rd IFO Long Term Storage Acceptance and Punchlist
DATE | 1st April 2015
SUB SYSTEM | ISC
RESP PERSON(s) | Corey
RELEVANT DOCS
ACCEPTANCE
ITEM NUMBER | ITEM | DEFINITION | COMMENTS | DCC NUMBERS / ICS | STATUS (NOTES) | SIGNED OFF 3rd IFO | DATE
1 | STORAGE PLAN REVIEW | Long Term Storage Requirements and Procedures are up to date. | For grouping of all Subsytem Storage Requirements Documents updated (see E1300001 ) | T1300027 |  | Corey Gray
2 | BOM REVIEW | Types and quantities of parts/assemblies/spares/tooling to be received by LTS are clearly understood. | Coordinate with LTS lead | E1500198 | DONE | Jodi Fauver | 18th Dec 2014
3 | CROSS CHECK | All Hardware (parts/assemblies/spares/tooling) checked into LAM. All in-vacuum parts have correct ICS information. | LAM=Long-Term Storage Asset Management (aka barcode system) | T1500119 | DONE | Jodi Fauver | 18th Dec 2014
4 | BOM RECEIVED | All assemblies/spares listed in BOM have been delivered to LTS custody. LTS lead has physical or virtual control of assemblies/spares. | Virtual custody means that any hardware still in use is checked into LAM/ICS for 3IFO but is checked out to responsible owner. | T1500119 | DONE | Jodi Fauver | 18th Dec 2014
5 | STORAGE VERIFICATION | Verification that Hardware is stored according to aLIGO and relevant substystem LTS plans. |  | T1500119 | DONE | Jodi Fauver | 18th Dec 2014
PUNCHLIST
ITEM NUMBER | DESCRIPTION | STATUS | VENDOR | RESP PERSON @ LHO | BUYER | DUE DATE | ADDITIONAL NOTES
1 | ISCTEY In Air Kitting | COMPLETE (lens missing, PZTs on order (due within 1-2months)) |  | Corey
2 | ISCTEX In Air Kitting | COMPLETE (PZTs on order (due within 1-2months)) |  | Corey
3 | Locate crate of (5) ISC HEPA filters (& a 6th HEPA) |  |  | Jodi/Corey
ITEMS STORED WITH NOTES/DEFECTS
1 | ASC RFPD ENCLOSURE, IN-VACUUM, TOP ASSEMBLY, LIGO-D1102002-v6 (4x) | Stored at CIT. Refer to LIGO-T1200506-v33. Serial number 249, 250, 639 & 640. | N/A | Rich Abbott
2 | LSC RFPD ENCLOSURE - MAIN BODY -v6, LIGO-D1101176-v6 (2x) | Stored at CIT. Refer to LIGO-T1200506-v33. Serial number 630 and 631. | N/A | Rich Abbott
3 | In-vacuum DCPD for OMC, LIGO-D060572-v1 (2x) | Stored at CIT. Refer to LIGO-T1200506-v33. Serial number 360 & 361. | N/A | Rich Abbott

## PSL
TITLE | 3rd IFO Long Term Storage Acceptance and Punchlist
DATE | 1st April 2015
SUB SYSTEM | PSL
RESP PERSON(s) | Rick / Peter K
RELEVANT DOCS
ACCEPTANCE
ITEM NUMBER | ITEM | DEFINITION | COMMENTS | DCC NUMBERS / ICS | STATUS (NOTES) | SIGNED OFF 3rd IFO | DATE
1 | STORAGE PLAN REVIEW | Long Term Storage Requirements and Procedures are up to date. | For grouping of all Subsytem Storage Requirements Documents updated (see E1300001 ) | LIGO-T1200557 | DONE | Rick Savage/Peter King | 20th June 2014
2 | BOM REVIEW | Types and quantities of parts/assemblies/spares/tooling to be received by LTS are clearly understood. | Coordinate with LTS lead | LIGO-E1200039 (pages 11-22) | DONE | Jodi Fauver | 20th June 2014
3 | CROSS CHECK | All in-vacuum parts have correct ICS information or an acceptable equivalent. All Hardware (parts/assemblies/ spares/tooling) quantities verified by LTS lead. | Parts will be put into LAM ASAP. LAM=Long-Term Storage Asset Management (aka barcode system) | Table T1500083 | DONE | Jodi Fauver | 20th June 2014
ISS T1500091
4 | BOM RECEIVED | All assemblies/spares listed in BOM have been delivered to LTS custody. LTS lead has physical or virtual control of assemblies/spares. | Virtual custody means that any hardware still in use is checked into LAM/ICS for 3IFO but is checked out to responsible owner. | Table T1500083 | DONE | Jodi Fauver | 20th June 2014
ISS T1500091
5 | STORAGE VERIFICATION | Verification that Hardware is stored according to aLIGO and relevant substystem LTS plans. |  | Refer to: T1500083 and T1500091 | DONE | Jodi Fauver | 18th Dec 2014
PUNCHLIST
ITEM NUMBER | DESCRIPTION | STATUS | VENDOR | RESP PERSON @ LHO | BUYER | DUE DATE | ADDITIONAL NOTES
ITEMS STORED WITH NOTES/DEFECTS
1 | Beam position sensitivity measurement hardware | MattH to deliver to 3rd ifo after using at LLO - checked out at LLO. Jodi ask Rick if this is the only set... |  | Matt H. |  | 2015-09-15
|  |  |  | Matt H. |  | 2015-09-15 | D1300901

## SEI
TITLE | 3rd IFO Long Term Storage Acceptance and Punchlist
DATE | 1st April 2015
SUB SYSTEM | SEI
RESP PERSON(s) | Mitch Robinson | Ken Mason
RELEVANT DOCS | E1500010, E1101149
RESOURCE DOCS | E1100331, E1100822, E1100369
ACCEPTANCE
ITEM NUMBER | ITEM | DEFINITION | COMMENTS | DCC NUMBERS / ICS | STATUS (NOTES) | SIGNED OFF 3rd IFO | DATE
1 | STORAGE PLAN REVIEW | Long Term Storage Requirements and Procedures are up to date. | For grouping of all Subsytem Storage Requirements Documents updated (see E1300001 ) | LIGO-T1200527 | DONE | Ken Mason | Dec 19th 2015
2 | BOM REVIEW | Types and quantities of parts/assemblies/spares/tooling to be received by LTS are clearly understood. | Coordinate with LTS lead | E1500010 | DONE | Jodi Fauver | 18th Dec 2014
3 | CROSS CHECK | All Hardware (parts/assemblies/spares/tooling) checked into LAM. All in-vacuum parts have correct ICS information. | LAM=Long-Term Storage Asset Management (aka barcode system) | T1500133 | DONE | Jodi Fauver | 18th Dec 2014
4 | BOM RECEIVED | All assemblies/spares listed in BOM have been delivered to LTS custody. LTS lead has physical or virtual control of assemblies/spares. | Virtual custody means that any hardware still in use is checked into LAM/ICS for 3IFO but is checked out to responsible owner. | T1500133 |  | Jodi Fauver | 18th Dec 2014
5 | STORAGE VERIFICATION | Verification that Hardware is stored according to aLIGO and relevant substystem LTS plans. |  | T1500133 | DONE | Jodi Fauver | 18th Dec 2014
PUNCHLIST
ITEM NUMBER | DESCRIPTION | STATUS | VENDOR | RESP PERSON @ LHO | BUYER | DUE DATE | ADDITIONAL NOTES
1 | (4) 4.50" conflat flanges with dual floating triax. SRI part number 960103-1 Rev B | Order placed 17th March 2015 | SRI Hermetics | Hugh Radkins (Ken Mason) | Marie Woods (MIT) | 10th April 2015
2 | Parts and Hardware | Ken is ordering D1003164 x3 5Kg masses. Hardware for H2 was not fully ordered. Balance of hardware needed, passed to Ken 3/31/15 |  | Ken Mason |  | Any day now. | Viton to be stored seperate w/desiccant.
3 | HAM - GS-13s | LLO is working on building these. 7 Hor, 4 Vert - Assembly essentially complete (needs to be tested) |  | Work being done at LLO. Joe Hanson and Jeremy Birch. |  |  | Essentially assembled - just awaiting leak and electrical test
4 | HAM - L4C's | LLO is working on building these. 6 Hor, 6 Vert - Assembly essentially complete (needs to be tested) |  | Work being done at LLO. Joe Hanson and Jeremy Birch. |  |  | Essentially assembled - just awaiting leak and electrical test
5 | HAM 1 Passive Stack | Gathering parts to final strorage location |  | Hugh |  |  | 2015-03-31 | Jodi barcode and tag
6 | Short list of Hepi items being fabricated by Brockmans. | Ordered. | Brockmans | Doug |  | 2015-03-31
7 | Feedthroughs | LLO is providing additonal components. Total short as of 3/19/15 is 12, 4 of these are noted in line item 0. |  |  |  | Shipped 3/30 from LLO
ITEMS STORED WITH NOTES/DEFECTS
1 | HEPI - Return all HEPIs from OSW | 1 remaining at OSW. No immediate plans to retrieve.
2 | HEPI - Remove Actuators as needed | Actuators need to be put on shelf and added to 1146 doc.
3 | HEPI - Deinstall H2 Hepi | Stored in place until further notice.
4 | HEPI - Crossbeams | 1 in Highbay, 3 at OSW. No immediate plans to retrieve. |  |  |  |  | Crossbeams at OSF will need to be flushed. The one in the Highbay is already done.
5 | Small amount of late arriving hardware/parts to be delivered to 3IFO dirty | Items will be listed and tagged as "dirty".
6 | HEPI Controller | Not delivered for 3rd IFO.
k | BSC 6 and 8 Feed thru's | Stored in place. |  | Jodi