## Slide 1: Advanced LIGO Commissioning Overview
Stanford LVC Meeting, August 27, 2014
Peter Fritschel

## Slide 2: History of Integrated Testing
Integrated testing phases interleaved with installation
Complementary division between LHO and LLO
  Designed to address biggest areas of risk as soon as possible
  H1 focused on long arm cavities; L1 worked outward from the vertex
July 2012
Oct 2012
Jan 2013
Apr 2013
July2013
Oct 2013
Jan 2014
Apr 2014
July2014
One Arm Test 1st arm cavity Green only
Input Mode Cleaner
HIFO-Y Y-arm + corner
Green + PSL IR
HIFO-XY
Both arms + corner
No AS port
Input Mode Cleaner with high power test
Dual recycled Michelson
I
II
III
H1
L1
Build & test from the arms backward
Build & test from the laser outward
Full Interferometer

## Slide 3: Current Timeline

## Slide 4: L1 Locking Statistics
157 locks lasting < 5 min
Most short locks broken because of commissioning work
Nearly 300 locks (> 1 min) since end of May
Longer locks came as more alignment DoF were globally controlled

## Slide 5: The First 3 Months

## Slide 6: Latest L1 Noise Budget & Range

## Slide 7: Subsystem highlights
Pre-Stabilized Laser (PSL) commissioned
Input Mode Cleaner (IMC) has been fully commissioned
All seismic isolators (SEI) work as designed and are fully automated
All suspensions (SUS) work as designed and are fully automated
Interferometer locking
  Following talks by Alexa and Den
Interferometer Automation
  Significant progress in implementing the Guardian state control system
  All subsystems, and full interferometer locking under Guardian control

## Slide 8: Commissioning focus for the first Observational Run
Target sensitivity
  Binary neutron star coalescence range of 40-80 Mpc, each detector
  Important frequency band: 20—300 Hz
  Input laser power: 25 W
Nominal duration
  3 months
Run start
  Some time in 2015, perhaps mid-2015

## Slide 9: Mysteries, unexpected problems, challenges: issues we likely need to address before the first science run

## Slide 10: Electro-static charging & actuation
Each End Test Mass has electro-static actuation, via electrodes on the adjacent reaction mass
Measurements of force vs bias indicates there is static charge present, equivalent to 10’s to several 100’s of volts
  ‘static’ charge will fluctuate and create noise
  Charge is not uniform; makes it hard to lower the bias for low noise
Work in progress: source of charging not clear, nor if it is constant
  First tests of a ‘de-ionizer’, connected to ETM chamber
  Procedure for discharging optic at installation has been vastly improved
Noise from ESD needs to be reduced: need factor of 3-5x for now
  Via bias reduction, or lower noise signal path, or both

## Slide 11: Laser intensity noise & coupling
Laser intensity stabilization is done in 2 stages
  Second stage detects a sample of the IMC transmitted light in vacuum, to reduce vibration related sensing noise
  Initial versions of the in-vacuum sensor had several design & assembly problems; essentially non-functional
  A new version that incorporates several design improvements has been made and installed in H1: testing is imminent
Typical ISS performance on L1, with temporary, in-air 2nd stage detector
The 250 Hz peak couples through to DARM
requirement

## Slide 12: Intensity noise coupling
Frequency (Hz)
Frequency (Hz)
10
100
1000
10
100
1000
Transfer function to arm cavity shows expected filtering:
Transfer function to OMC readout does not …
Work in progress trying to understand this coupling, through measurements and modeling
  Higher order modes? Offsets? RF sidebands?
model
model
measurement
measurement

## Slide 13: Suspension violin modes
Test mass suspension violin modes, at 500 Hz, are excited several orders of magnitude above thermal
We do not understand why they are vibrating so much
Prevents us from engaging full whitening on the GW readout channels: excess ADC noise
Need to actively damp the modes, using interferometer signal to feed back to the quad penultimate stages
  Should be doable, but it is tricky: 16 very high Q modes in a narrow frequency range
  Some progress recently on L1 with the DRMI
Violin mode amplitude
Feedback signal
excitation
damping

## Slide 14: Glitches from digital-to-analog converters
DAC transitions are accompanied by a glitch
  Inevitable in all DACs (12 nV-sec spec for our DACs)
  Largest at the zero-crossing (all bits flip), next largest at ¼ & ¾ of full scale
Observed to create low frequency noise in the recycling cavity signals
Control signal
Error signal
Noise mechanism not completely clear
Solutions:
Offsets on control signals
Low pass filters after DAC
Also an issue for ESD feedback, at ¾ range transition

## Slide 15: Parametric Instabilities
Combination of high stored optical power and low mechanical loss could cause an instability
Nascent
Excitation
Mechanical
Mode
Radiation
Pressure
Pump
Field
Scattered
Field
(cavity gain)
f
High Finesse
Cavity
Latest analysis (S Gras) suggests we are more prone to PI than we thought
  MC simulation with distribution of RoC’s and acoustic mode frequencies of test masses
Start to look for risky modes even before they become unstable (UWA idea)

## Slide 16: Seasonal variability of ground motion
microns/second
1
0
2
3
4
5
6
7
rms in:
0.1—0.3 Hz
0.3—1 Hz
July
Aug
Sep
Oct
Dec
Nov
Jan
Feb
Apr
Mar
May
June
June
So far, commissioning has been during periods of low microseism
LLO ground motion over 500 days

## Slide 17: Impact of higher ground motion
Arm Length Stabilization could suffer
  Arm cavity finesse at 532 nm is much lower than desired:
    ETMs have too large a transmission at 532 nm
    Finesse: 5-10 (actual) vs. 100 (desired)
  Makes the cavity locking point much more sensitive to alignment and alignment fluctuations
Replacing the ETMs could be the best solution
  ETMs now coming out of LMA have the right 532 nm transmission
  Downside would be a 2 month hit for replacement

## Slide 18: In Conclusion
Initial commissioning has progressed quickly
  The only significant delay was due to the green coating issue.
Next up: get H1 caught up with L1
  H1 will test some ideas for improving the locking scheme
  H1 has the improved second stage detector for the laser intensity stabilization in place
L1 has reached the aLIGO Project milestone for integration: 2 hour lock
  As a result, non-LIGO Lab people can now contribute to L1 commissioning, without having to set up a contract with aLIGO