## Sheet1
Priority | When: | Lead: | LLO Post O1 EE Tasks Description | sub system: | Notes: | bugzilla #: | ECR
| Need to coordinate with Janeen and Brian O | Michael L. | 71 MHz seperate oscillator for SEI CPS | SEI | Need full IFO, so during commissoning phase
| Emailed | Carl | SEI Coil Driver hardware watch dog WD modifications and cable install | SEI | Radar to do? | Bug 1011 | HowtoinstalltheDriverCutoffboardsinaCoilDriver.pdf
| Emailed | Michael L. | 18 Bit DAC upgrade | SUS | Need 5 more cards (emailed RM) | 945 | E1500217
| Emailed | Carl | AA/AI filter board update to v6 | SUS |  | 463 | 919
|  | Carl | swap out pre-production PI electronics for production ones | SUS | Need to complete testing of new units
|  | Carl | LV ESD DCN (cap change) DCN E1500443 | SUS |  |  | E1500341
|  | Carl | LV ESD new whitening board and front panel | SUS |  |  | E1500417
| Emailed | Carl | ITM ESD vacuum feed through modifications | SUS | During vent! | Bug 907 | E1400399
| Aprilish | Carl | ITM LV ESD Design and install (Aprilish) | SUS
|  | Carl | ECR: Upgrade monitor channels on the Low-noise, Low-voltage Electro-static Driver | SUS
|  | Carl | Move SUS ITM Feild racks to proper location and rearange chassis to match drawings | SUS
|  | Carl | L1 ITMY (QUAD) L1 (UIM) UR channel actuation failure | SUS | See spsh ECRS Issues Bugs | 871 | https://services.ligo-wa.caltech.edu/integrationissues/show_bug.cgi?id=871
| Emailed | Carl | ITMX (D1200059) Cables #56=F3-2C1=UIM & #57=F3-2c2=PUM wrong in-Vac | SUS
|  | Carl | Install ISC Auxiliary Signals Concentrator 6 in End station ISC feild racks | ISC | Need to move Picomotor and PD amps to optic table or sus rack | 923 | E1400311-v2
|  | Michael L. | RF coupling modificatons? | ISC | Requires IFO commissioning time, and PSL access
|  | Adam | connect RT system to Beckhoff | ISC
|  | Adam | install the relay switch for the ALS laser noise eater at Xend | ISC |  | 716
|  | Carl | EtherCAT Corner Station Chassis 6; his is for adding the EOM drivers beckhoff terminals | ISC |  | 937 | E1500135
|  | Michael L. | VCO modifications | ISC
|  | Michael L. | TCS RF install PP in LVEA, Beckhoff cable from R1 to CER, Coax from AOM distro amp to timing comparator in CER | TCS | Need to find or order cable of appropriate length | Bug 1008 | E1500180-v1
|  | Michael L. | TCS laser controller swap out locks | TCS
|  | Michael L. | TCS RF PP in field racks | TCS
|  | Carl | TCS laser chiller summing chassis (D1500268) install | TCS |  |  | ECR E150038-v1
|  | Carl | Investigate TCS RTD sensors that are not working? | TCS
| Emailed | Michael L. | upgrade PEM microphones? | PEM | Jeremy to install cabling |  | ECR 1500412
|  | Michael L. | seperate timing DCPS at ends? | PEM | ECR / justification
|  | Michael L. | install EOM D0900760 (PSL/ISC) | PSL | need from H1, no other info
| Still need this? | Carl | Timing work? Fiber install at End Station | CDS | Check with Keith if still needed?
|  | Michael L. | Install 485 bus in LVEA for dust monitors | CDS | Jeremy to install cabling Can Comtrol do multidrop? |  | R1500018-v4
| Yep |  | Inspect LV ESD Drivers ETMX, ETMY |  | look for stuff that doesn't belong
|  | Carl | beckhoff terminals/power supplies/ and new rear panel for the EtherCAT Corner Station Chassis 6. | ISC
Cables to Pull: |  | Designation | From: | To:
coax |  | AOM ~40mhZ to comparator | TCS-R1 | ISC-C3
DB 25 |  | AOM ~40mhZ to Beckhoff | TCS-R1 | ISC-C2
DB37 |  | SUS HWWD | SUS-XC1 | SUS-XR1
DB37 |  | SUS HWWD | SUS-YC1 | SUS-YR1
DB37 |  | SUS HWWD | SUS-C5 | SUS-R5
DB37 |  | SUS HWWD | SUS-C5 | SUS-R6